COMPOSITE ANNUAL ACTION PLAN 2023

| Programme Area (PBB) | Sub-Programme(PBB) | No. | Broad Activities | Location | Baseline | Output Indicators | Quarterly Time schedule |  |  |  | Programme status |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 1st | 2nd | 3rd | 4th | New |  | Ongoing |  | GoG | DACF | IGF | Donor | Lead | Collaborating |
| Thematic Area/Development Dimension: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Agricultural Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Services and management Agricultural Services and management | 1 | Service operational activities (utilities, office consumables, fuel and; insurance and road worthy) | Goaso | 12 Utilities, 16 Office consumables,100 gallons of fuel,15 insurance and 1 road worthy were incured | Expenditure on operational activities | * | * | * | * |  |  | ✓ |  | 1,500 |  |  | 3,000 | Dept. of Agric. | Fin Dept., CAD, CIDA |
|  |  | 2 | Conduct monitoring and Evaluations activities | Municipal wide | 18 monitoring and eveluations conducted | No. of Monitoring and Evaluation activities conducted | * | * | * | * |  |  | ✓ |  | 7,000 |  |  | 18,000 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 3 | Establishment 60 of field demonstrations | Municipal Wide | 14 maize, 14 rice and 14 vegetable demostrations were establised | Number of maize, Rice and Vegetables demonstration fields established | * | * | * | * |  |  | ✓ |  | 700 | 30,000 | 30,000 | 2,000 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 4 | Organize 8 farmer based trainings | Municipal Wide | 4 farmer trainings were conducted | farmer trainings were conducted |  | * | * | * |  |  | ✓ |  | 1,000 |  |  | 2,000 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 5 | Organize 2 RELC planning session | Municipal Wide | 2 | RELC planning Sessions conducted | * | * | * | * |  |  | ✓ |  | 1,300 |  |  | 1,500 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 6 | Maintain 1 official vehicle and 14 motor bikes | Municipal Wide | 1 official vehicle 14 motor bikes were maintained | official vehicle and motor bikes were maintained | * | * | * | * |  |  | ✓ |  | 1,000 |  |  | 2,200 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 7 | Conduct 2 survey activities | Municipal Wide | 2 surveys conducted | surveys conducted |  | * | * |  |  |  | ✓ |  | 1,000 |  |  | 1,594.33 | Dept. of Agric. | Fin Dept, CAD, CIDA |
|  |  | 8 | Organise Stakeholder engagement with the Mim Traditional Council on the tourist potentials of the Mim Bour | Mim |  | Meeting organised |  | * |  |  | ✓ |  |  |  |  |  | 3,000 |  | CAD | MTC, Tourism Authority |
|  |  | 9 | Update the list of hospitality industries (hotels and Restaurants) in the Municipality | Municipal Wide |  | No of hotels and restaurants updated |  |  |  | * |  |  | ✓ |  |  |  | 500 |  | CAD | Tourism Authority |
| Economic Development | Trade, tourism and industrial development | 8 | Build capacities of MSMEs (no) through technical and management training | Municipal Wide | 8 | No. of technical training conducted No. of Management training conducted | * | * | * | * |  |  | ✓ |  | 24,000.00 |  |  |  | BAC | CAD, Fin Dept, NBSSI, GRATIS, |
|  |  | 9 | Build capacity of MSMEs in Financial Management and access to financial support | District wide | 4 trainings organised | No. of financial management training conducted/No. of MSMEs accessed financial support | * | * | * | * |  |  | ✓ |  | 12,000.00 |  |  |  | BAC | CAD, Fin Dept, NBSSI, GRATIS, |
|  |  | 10 | Conduct Business Fora to Bridge the gap between the Municipal Assembly and the business community | Goaso | 2 | No. of Business Fora conducted | * |  | * |  |  |  | ✓ |  |  | 16,000.00 |  |  | BAC | CAD, Fin Dept, NBSSI, GRATIS, |
| Economic Development | Trade, tourism and industrial development | 11 | Update business inventory and register/database (referenced with property Addressing-SNAPS | Municipal wide | - | Number of business inventory and register/database updated | * | * | * | * | ✓ |  |  |  |  |  |  | 37,142.86(UDG) | BAC | CAD |
|  |  | 12 | Review 2016-2021 LED Strategic Plan and prepare 2022-2024 LED Strategic | Goaso |  | Enhanced implementation of LED activities -Increase growth in Local economic activities -Increased Job creation/employment opportunities -Growth in the Local economy | * | * | * | * | ✓ |  |  |  |  |  |  | 18,571.43(UDG) | BAC | CAD |
| Economic Development | Trade, tourism and industrial development | 13 | Hold 2No. LED Fora with local private sector community/businesses on strategies to business development and economic growth | Goaso/Mim | 2 | Number of LED with local private sector community conducted | * | * | * | * |  |  | ✓ |  |  |  |  | 32,500(UDG) | BAC | CAD, NBSSI |
|  |  | 14 | Review and prepare annual business support action plan | Goaso |  | Number of annual business support action plan reviewed and prepared | * | * | * | * |  |  | ✓ |  |  |  |  | 18,571.43(UDG) | BAC | CAD, NBSSI |
|  |  | 15 | Review and update Annual Revenue Improvement action plan | Goaso | 1 | Annual Revenue improvement Action Plan reviewed and updated | * | * | * | * |  |  | ✓ |  |  |  |  | 11,142.85(UDG) | BAC | CAD, NBSSI |
| Economic Development | Trade, tourism and industrial development | 16 | Redevelop Wednesday Market into Daily Market to include: Construction of 150No. Market Stalls, 150No. Lockable Stores, Pavement of Market Area (24,000M2), Covering of Market Drains (730M), Improvement of access roads to market (750M surface bitumen) Construction of 1No. Crèche, 1No. Sick Bay, 1No.-Fire Post, 1No. 10-Seater WC Toilet and Urinal (6 Cubicles), 1No. 8-Unit Shower Bathrooms, Provision of 50No. Waste Bins, 2No. Skip Containers (6M3), Construction of Abattoir and Drilling and Mechanization of 1No. Borehole with Installation of Polytank (5,000 litres) | Abotanso |  | Number of stalled and stores constructed,market area paved, crèche, sick bay and Abbatior contructed includind a mechanised borehole | * | * | * | * | ✓ |  |  |  |  |  |  | 8,292,436.7(UDG) | MA | Wks Dept, Market Women, Traditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |
| Economic Development | Trade, tourism and industrial development | 17 | Redevelop Daily Market and Old Station into a Shopping Complex: Construction of Mall, Restaurant, Conference Room, with Parking Construction of 100No. Lockable Market Stores, with Pavement of the Total area (18,000M2) 1No. 10-Seater WC Toilet and Urinal (6 Cubicles), Provision of 15No. Waste Bins and 1No. Skip Container (6M3) and Installation of Complete Luminous 10No. LED Security Lights) | Manhyia, | - | Redevelopment of the daily market into a shoping complex completed | * | * | * | * | ✓ |  |  |  |  |  |  | 11,145,373.2 (UDG) | MA | Wks Dept, Market Women, Assembly MembersTraditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |
| Thematic Area/Development Dimension: Social Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Social Welfare & Community Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare & Community Development | 18 | Supervise 15 juveniles placed under trained probationers | Asumura,Akrodie,Asanteman council, Dominase | 9 juveniles were placed under probation | Number of juveniles supervised | * | * | * | * |  |  | ✓ |  | 500.00 |  | 500.00 |  | DSWCD | MGCSP, HOLGS, RCC, Ghana police service, NGO’s, Judicial service, EYS DEPT |
|  |  | 19 | Conduct Investigations and submit 12 Social Enquiry Reports to the Juvenile Court | Municipal wide | - | Number of staff/agents trained on probation issues | * | * | * | * |  |  | ✓ |  | 750.00 |  | 750.00 |  | DSWCD | Family &Tribunal Court, MGCSP, HOLGS |
|  |  | 20 | Organize training for street Naming and Property Addressing Team and Technical Officers on SNPAS and LUPMIS. | Goaso | - | Number of trainings for street naming and property addressing team organized | * | * | * | * | ✓ |  |  |  |  |  |  | 37,142.85 (UDG) | DSWCD | MGCSP |
|  |  | 21 | Form and train 15 new child protection committees in 15 communities | Municipal wide | 5 child protection committee | Number of protections on committees formed and trained | * | * | * | * |  |  | ✓ |  | 1,000.00 |  | 1,000.00 |  | DSWCD | MGCSP, MA, Media, CSO, Traditional Authorities, Ghana Police, EYS DEPT, GHS. |
|  |  | 22 | Reconcile 220 Family related issues | Municipal wide | 180 family related issues reconciled | Number of family related issues reconciled | * | * | * | * |  |  | ✓ |  | 1,000.00 |  | 1,000.00 |  | DSWCD | MGCSP, MA, Media, CSO’s, Traditional Authorities, Ghana police , EYS DEPT, GHS |
|  |  | 23 | Embark on Monitoring & Evaluation of 20 Early Childhood Development Centres within the Municipality. | Municipal wide | 15 early childhood development centers monitored and supervised | No. of early Childhood Development Centres monitored | * | * | * | * |  |  | ✓ |  | 1,000.00 |  |  |  | DSWCD | Ghana Police, EYS DEPT, GHS |
|  |  | 24 | Intensify Education (radio, community sensitizatation.) on Effect of Early Child Marriage & Teenage Pregnancy especially in Rural & settler Community | Municipal wide | Organise 7 radio programmes on early child marriage and teenage pregnancy | No. of Early Child MarriaEYS Dept and Teenage Pregnancy education/sensitisations conducted | * | * | * | * |  |  | ✓ |  | 500.00 |  | 1,000.00 |  | DSWCD | MGCSP, MDE, MDH, MA, Media, CHRAJ, Legal Aid, CSO’s. |
|  |  | 25 | Organize 10 Mass Education on The Children’s Act and Domestic Violence Act using Community Durbar and Radio Panel Discussion | Municipal wide | Organise 7 radio programmes on early child marriage and teenage pregnancy | Number of Public Educations carried out | * | * | * | * |  |  | ✓ |  | 500.00 |  | 1,500.00 |  | DSWCD | MA, Security Agencies, Assembly Members, CSO’s, Decentralize Departments, Traditional, Authorities, Communities |
|  |  | 26 | Update Data on Persons with Disability (PWD’s) | Municipal wide | 100 PWD’s | Number of PWD’s registered | * | * | * | * |  |  | ✓ |  | 842.00 |  |  |  | DSWCD | MA, PWD’s, & Other Decentralize Department |
|  |  | 27 | Monitor & Supervise 44 LEAP Communities and it’s Pay-point Centres | Municipal wide | 40 | Number of Beneficiaries Paid & Monitored | * | * | * | * |  |  | ✓ |  | 600.00 |  |  |  | DSWCD | MA,Ghana Police Service, Bank Officials |
|  |  | 28 | Train Selected Groups of PWD’s on Beads Making & Bee keeping under | Municipal wide | Train 45 pwds on beads making and Bee keeping | Number of PWD groups Empowered |  |  |  |  | ✓ |  |  |  | 1,000.00 |  |  |  | DSWCD | MA, PWD’s, & MGCSP |
|  |  | 29 | Sensitize persons with disability (PWD’s) on gender-based violence &its related issues | Municipal wide | Sensitize 35 persons with disability on gender based violence | Number of persons with disability (PWD) on gender-based violence sensitized | * | * | * | * |  |  | ✓ |  | 3,700.00 |  |  |  | DSWCD | MA, PWD’s, & MGCSP |
|  |  | 30 | Organise 4 quarterly advocacy programmes to enhance participation in decision-making for women and girls with disability | Municipal wide | 3 advocacy programmme organised | No. of quarterly advocacy programmes organized for women and girls with disability | * | * | * | * | ✓ |  |  |  |  |  |  |  | DSWCD | NCCE, MoGCSP, Traditional Leaders, CSO’s, MA |
|  |  | 31 | Organise 14 community dialogues, clinics, durbars, and workshops to sensitize women and girls with disability including mental health | Municipal wide | 11 community dialogues and workshop to sensitize women and girls | Number of community dialogues, clinics, durbars, and workshop to sensitize women and girls with disability reorganized | * | * | * | * | ✓ |  |  |  |  |  |  |  | DSWCD | NCCE, MoGCSP, Traditional Leaders, CSO’s, MA ,GHS |
|  |  | 32 | Provide guidance and counselling, social support services to victims of Gender-Base violence with disability including those with mental health conditions | Municipal wide | - | No. of PWD victims of Gender-Based violence Counselled and supported | * | * | * | * | ✓ |  |  |  |  |  |  |  | DSWCD | NCCE, MoGCSP, Traditional Leaders, CSO’s, MA ,GHS |
|  |  | 33 | Build capacity of 20 persons with disability to be able to report perpetrators of gender based violence | Municipal wide | 17 persons with disability have been given the s | No. of reported cases of Gender-Based violence by persons living with disability | * | * | * | * | ✓ |  |  |  |  |  |  |  | DSWCD | NCCE, MoGCSP, Traditional Leaders, CSO’s, MA ,GHS |
| Focus Area: Education, Youth And Sports Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, Youth And Sports Services | 34 | Complete Construction of 1No.3-unit classroom block with staff common room, store 4-seater aqua privy toilet and provision of furniture at SDA school | Goaso |  | Level of construction and furnishing of Classroom block | * | * |  |  |  |  | ✓ |  |  |  | 90,721,71 |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 35 | Complete construction of 7 No. 3-unit classroom block, staff common room, store, 4-seater aqua privy toilet and provision of furniture | Anyinmaye M/A primary school, Ampenkro-Koforidua, Ampenkro,Kofimirekrom, Bediako, Gyesewobre, Fawohoyeden Methodist Primary A, Ahafoman JHS, Gyasikrom, Mfama, Aworokrom |  | No. of classroom blocks completed and furnished | * | * | * | * |  |  | ✓ |  |  | 656,436.46 |  |  | EYS DEPT | CAD, Works Dept |
|  |  | 36 | Complete construction of first floor of 2 storey hostel with 120 dual beds for NTS | Goaso |  | Level of construction and furnishing | * | * | * | * |  |  | ✓ |  |  | 62,265.62 |  |  | EYS DEPT | CAD,Works dept |
|  |  | 37 | Complete construction of 1 No. 6 unit classroom block with suspended ground floor slap | Mim SHS | 75% | Level of construction of Classroom block | * | * | * | * |  |  | ✓ |  |  | 360,917.78 |  |  | EYS DEPT | CAD,Works dept |
|  |  | 38 | Complete construction n of 1 No. 2 unit kindergarten classroom block at | Mim Presby | 1 |  | * | * | * | * |  |  | ✓ |  |  | 77,035.10 |  |  | EYS DEPT | CAD,Works dept |
|  |  | 39 | Provide 1000 dual desks,500& 167 Hexagonal desk for public basic schools | Municipal Wide | - | 4000 dual desks and 3000 mono desk provided for public basic schools |  |  | * | * |  |  | ✓ |  | 300,000.00 | 200,000.00 |  | 200,000(DACF-RFG) | EYS Dept | CAD Dept , Fin Dept, Works Dept |
|  |  | 40 | Construct 10No. Toilet & Urinal Facilities for Schools | Selected schools |  | No. of toilet and urinal facilities constructed |  |  | * | * | ✓ |  |  |  |  | 250,000.00 |  | 500,000.00 | EYS Dept | CAD,Fin Dept, Works Dept, IRC. World Vision |
|  |  | 41 | Provide potable and safe water for 10 Schools | Selected schools |  | No of schools provided with potable and safe water |  |  | * | * | ✓ |  |  |  |  | 40,000.00 |  | 160,000 | EYS Dept | CAD,Fin Dept, Works Dept, IRC. World Vision, Aquaya Institute, Safe Water Network |
|  |  | 42 | Provide 10 wheel chairs, 10 clutches, 50 glasses and 50 hearing aids for students/pupils with disabilities | Selected schools |  | 10 wheel chairs, 10 clutches, 50 glasses and 50 hearing aids provided for students/pupils with disabilities |  |  | * | * | ✓ |  |  |  |  | 10,000.00 | 10,000.00 |  | EYS Dept | CAD, Fin Dept, DSWCD |
|  |  | 43 | Organize common test in literacy and numeracy for primary two and four children. | Municipal Wide |  | common test in literacy and numeracy for primary four and six children organized |  |  |  | * |  |  | ✓ |  |  | 10,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 44 | Organize capacity-building workshop for teachers in ICT and core subjects | Goaso | 1 | Number of capacity-building workshop for teachers in ICT and core subjects organized |  | * |  |  |  |  | ✓ |  |  | 20,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 45 | Organize Science, Technology, Mathematics and Innovative Education (STMIE) clinic | Municipal Wide | 1 | Number of Science, Technology, Mathematics and Innovative Education (STMIE) clinic organized |  | * |  |  |  |  | ✓ |  |  | 25,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 46 | Organize Best teacher and worker awards for deserving teachers/workers | Goaso |  | Best teacher and worker awards for deserving teachers/workers organized |  |  | * |  |  |  | ✓ |  |  | 50,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 47 | Conduct regular monitoring & supervision in all public basic schools | Municipal Wide |  | No. of monitoring/supervisions conducted. No. of public basic schools monitored/supervised | * | * | * | * |  |  | ✓ |  |  | 30,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 48 | Conduct regular payroll audit in all schools | Municipal Wide |  | Number of regular payroll audit in all schools conducted |  |  | * |  |  |  | ✓ |  |  | 10,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 49 | Conduct comprehensive inspection of school and issue report | Municipal Wide |  | Number of comprehensive inspection of school conducted and report issued | * | * | * | * |  |  | ✓ |  |  | 30,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 50 | Organize school level SPAM/durbar in all schools | Municipal Wide |  | School level SPAM/durbar organized in all schools |  |  |  | * |  |  | ✓ |  |  | 8,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 51 | Organize workshop for DEO staff and headteachers on financial and administrative practices to strengthen accountability and transparency | Municipal Wide |  | Number of workshops for DEO staff and headteachers on financial and administrative practices to strengthen accountability and transparency organized |  |  | * |  |  |  | ✓ |  |  | 5,000.00 |  |  | EYS DEPT | CAD, Fin Dept |
|  |  | 52 | Provide 20 executive office chairs and desks for municipal education office | Municipal Wide |  | 20 executive office chairs and desks provided for municipal education office |  | * |  |  | ✓ |  |  |  |  | 20,000.00 |  |  | EYS DEPT | CAD, Fin Dept, Works Dept |
|  |  | 53 | Provide schools with essential supplies - (TLMs) markers, cardboard supplementary readers etc | Municipal Wide |  | Number of teaching learning materials provided for schools | * |  |  |  | ✓ |  |  |  |  | 5,000.00 | 10,000 |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 54 | Conduct reading competition at the public basic schools | Municipal Wide | 1 | Reading competition at the public basic schools conducted |  | * |  |  |  |  | ✓ |  |  | 30,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 55 | Conduct Mock Exams for JHS 3 Students | Municipal Wide | 1 | Number of Mock Exams for JHS 3 Students conducted |  | * |  |  |  |  | ✓ |  |  | 25,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 56 | Organize my first day at school | Municipal Wide | 1 | Number of sensitizations organized at schools | * |  |  |  |  |  | ✓ |  |  | 10,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 57 | organize orientation for newly trained teachers | Municipal Wide |  | Number of orientation for newly trained teachers organized |  |  |  |  |  |  | ✓ |  |  | 15,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 58 | Organize ( inter-school sports and athletic competition (within and outside circuit and district) | Municipal Wide | 1 | Number of inter-school sports and athletic competition organized within and outside circuit and district |  | * |  |  |  |  | ✓ |  |  | 40,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 59 | Organize enrolment drive in communities prior to reopening of schools | Municipal Wide |  | Number of Enrolment drive in communities prior to reopening of schools organized | * | * | * | * |  |  | ✓ |  |  | 10,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 60 | Support girls by providing a life-skills development programme | Municipal Wide | 1 | Number of girls provided with life-skills development programmes | * | * | * | * |  |  | ✓ |  |  | 5,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 61 | Promote activities of female mentors (Teachers, Community women and older girls) to mentor girls | Municipal Wide |  | Activities of female mentors (Teachers, Community women and older girls) to mentor girls promoted |  |  |  |  |  |  | ✓ |  |  | 5,000.00 |  |  | EYS DEPT | CAD, Fin Dept, |
|  |  | 62 | Provide incentive packaEYS Dept for teachers in deprived areas | Municipal Wide |  | Teachers in deprived areas provided with number of incentive packaEYS Dept | * | * | * | * |  |  | ✓ |  |  | 5,000.00 | 5,000.00 |  | EYS Dept | CAD, Fin Dept, |
|  |  | 63 | Provide financial assistance to needy but brilliant students | Municipal Wide |  | Financial assistance to needy but brilliant students provided | * | * | * | * |  |  | ✓ |  |  | 86,001.86 |  |  | EYS Dept | CAD, Fin Dept, |
| Social Service Delivery | Sports services | 64 | Construction of multi –purpose court ( volley ball, Basketball, hand ball) | Goaso | - | Multi-purpose court constructed | * | * | * | * | ✓ |  |  |  |  | 10,000.00 | 10,000.00 | 40,000.00 | NSA | EYS DEPT, GKA, ARVA, ANMA, GTC |
|  |  | 65 | Organize May Day Games for workers | Goaso | 1 | May Day Games organized |  | * |  |  |  |  | ✓ |  |  | 1,000.00 | 2,000.00 | 4,000.00 | NSA | ANMA, Media, GTC |
|  |  | 66 | Organize Volleyball League | Municipal Wide | 1 | Volley ball league organized | * | * | * | * |  |  | ✓ |  |  | 1,000.00 | 1,000.00 | 3,000.00 | NSA | ANMA, ARVA, EYS DEPT |
|  |  | 67 | Supervise inter- School Games | Municipal Wide | 30 | Inter-school games supervised |  | * | * |  |  |  | ✓ |  |  | 500.00 | 300.00 |  | NSA | ANMA, ARVA, EYS DEPT |
|  |  | 68 | Organize keep fit Games | Municipal Wide | 4 | Keep Fit games organized | * | * | * | * |  |  | ✓ |  |  | 5,000.00 | 500.00 | 4,000.00 | NSA | GKA, ANMA, GHS, Media |
|  |  | 69 | Supervise Second Division League | Municipal Wide | 20 | Second Division League Organized |  | * | * | * |  |  | ✓ |  |  | 500.00 | 500.00 |  | NSA | ANMA, Media |
|  |  | 70 | Host 150 Radio education programs | Municipal Wide | 90 | Radio education programs organized | * | * | * | * |  |  | ✓ |  |  |  |  | 500.00 | NSA | Media |
| Focus Area: Public Health Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Public Health Services and Management | 71 | Visit to Communities, Schools & Institutions for Registration | Municipal Wide | - | Communities, schools and Institutions registered | * | * | * | * |  |  | ✓ |  |  |  |  |  | NHIA | MA |
|  |  | 72 | Support the Municipal HIV/AIDS Committee Response Initiative | Municipal Wide | - | Municipal HIV/AIDS Committee Response Initiative supported | * | * | * | * |  |  | ✓ |  |  |  |  |  | MA | GHS |
|  |  | 73 | Complete construction of Maternity ward at | Asumura | 1 | construction of Maternity ward completed | * | * | * | * |  |  | ✓ |  |  | 91,105.57 |  |  | MA | GHS |
|  |  | 74 | Complete construction of 1 No. CHPS compound at | Ayomu Manhyia | 1 | Construction of 1 No. CHPS compound completed | * | * | * | * |  |  | ✓ |  |  | 59,844.01 |  |  | MA | GHS |
|  |  | 75 | Complete infrastructural projects in the constituency by the Hon. MP | Constituency Wide | - | Infrastructural projects in the constituency completed | * | * | * | * |  |  | ✓ |  |  | 180,000.00 |  |  | MA | GHS |
|  |  | 76 | Complete construction of 4 No. weighing centers at | Mim Domeabra, Essienipong, Dankwakrom and Nyankomago | 4 | Construction of 4 No. weighing centers completed | * | * | * | * |  |  | ✓ |  |  | 6,066.50 |  |  | MA | GHS |
|  |  | 77 | Complete construction of 1 No. 4 seater WC toilet with urinals at | Goaso Abotanso | 1 | Construction of 1 No. 4 seater WC toilet with urinals completed | * | * | * | * |  |  | ✓ |  |  | 6,989.04 |  |  | MA | GHS |
|  |  | 78 | Support the Municipal Health Directorate to organize Roll Back Malaria Programmes | Municipal Wide | - | Municipal Health Directorate to organize Roll Back Malaria Programme supported | * | * | * | * |  |  | ✓ |  |  | 21,500.47 |  |  | MA | GHS |
|  |  | 79 | Support Health Programme (Maternal and Child Health Outreach and National Immunization Programme) | Municipal Wide | - | Health Programme (Maternal and Child Health Outreach and National Immunization Programme) supported | * | * | * | * |  |  | ✓ |  |  | 30,000.00 |  |  | MA | GHS |
|  |  | 80 | Conduct Monthly social and risk communication in the Municipality | Six Sub-district | 98 | Public Sensitized | * | * | * | * |  |  | ✓ |  | 54000 |  |  |  | GHS | MEDIA |
|  |  | 81 | Intensify school heath service in (20 JHS and 20 Primary School) | Six Sub-district | 11% | school health activities conducted | * | * | * | * |  |  | ✓ |  | 6000 |  |  |  | GHS | EYS DEPT |
|  |  | 82 | Increase Education on Family planning acceptor rate | Six Sub-district | 55% | Create awareness on F/P and provide services on various methods | * | * | * | * |  |  | ✓ |  | 8000 |  |  |  | GHS | MEDIA |
|  |  | 83 | Capacity building of staff for effective service delivery and surveillance activities | Four Sub-districts | 4 | Training and refresher training on data management and report writing | * | * | * | * |  |  | ✓ |  | 75,000 |  |  |  | GHS | MA |
|  |  | 84 | Organise Safe motherhood activities twice in the year | Four sub-Municipal | - | Safe motherhood activities organised | * | * | * | * |  |  |  |  | 30000 |  |  |  | GHS | MA |
|  |  | 85 | Conduct EPI activities | Six Sub-district | - | To strengthen routine Immunizations | * | * | * | * |  |  | ✓ |  |  |  |  |  | GHS | MA |
|  |  | 86 | Conduct quarterly monitoring Supervision | Six Sub-district | 4 | Monitoring and Supervision conducted | * | * | * | * |  |  | ✓ |  | 30000 |  |  |  | GHS | MA |
|  |  | 87 | Conduct TB Case detection and screening on daily basis | Six Sub-district | 45% | TB screening conducted | * | * | * | * | * |  | ✓ |  | 30000 |  |  |  | GHS | MA |
|  |  | 88 | Organise HIV/AIDS control and management in the district | Two Sub-district | - | Creating ART sites at two health Centers | * | * | * | * | * |  | ✓ |  |  |  |  | 20000 | GHS | JSI, MA |
|  |  | 89 | Conduct PMTCT/HTC monthly | Six Sub-district | - | HTC services | * | * | * | * |  |  | ✓ |  | 2000 |  |  |  | GHS | MA |
|  |  | 90 | Extension of nutrition friendly school initiative to 24 schools within the municipality | Schools selected across the six sub district | 24 |  | * | * | * | * |  |  | ✓ |  | 27000 |  |  |  | GHS | EYS DEPT,MA |
|  |  | 91 | Organise community and radio education in NHIS | Municipal Wide | - | Number of community and radio education in school organized | * | * | * | * |  |  | ✓ |  |  | 5,000.00 |  |  | NHIA | CAD, Media |
|  |  | 92 | Repairs of Office Equipment | Goaso | - | Office equipment repaired | * | * | * | * |  |  | ✓ |  |  |  |  |  | NHIA | CAD |
| Social Service Delivery | Information Services | 93 | Public Sensitization on Government Policies, Assembly’s Budget fees and fines & all activities | Municipal Wide | - | The Public Sensitized | * | * | * | * |  |  | ✓ |  |  |  | 2,500 |  | ISD | CAD, Media |
|  |  | 94 | Publications of development activities of the Assembly on TV, Radio & Online | Municipal Wide | - | Development Activities published | * | * | * | * |  |  | ✓ |  |  |  | 2,950 |  | ISD | CAD, Media |
| Thematic Area/ Development Dimension: Environment, Infrastructure, and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Environmental health and sanitation services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment , Infrastructure, and Human Settlement | Environmental health and sanitation services | 95 | Conduct house to house inspections in 40 communities | Goaso, Mim, Asumura, Kasapin, Dominase,akrodie | 33 | Improved household hygiene, Reports | * | * | * | * |  |  | ✓ |  |  |  | 4,000.00 |  | CAD (EHU) | MA,Zoomlion,traditional authorities, households, communities |
|  |  | 96 | Conduct 6 radio programs and 40 on information centre on good sanitation and hygiene practices | Goaso, Mim, Asumura, Kasapin, Dominase,akrodie, pomaakrom,fawohoyeden | 4 radio programs, 32 community program | No. of radio and community programs conducted on good sanitation and hygiene practices | * | * | * | * |  |  | ✓ |  |  |  | 4,000.00 |  | CAD (EHU) | Zoomlion, MDH,MDE,Traditionalauthorities,communities |
|  |  | 97 | Screen 500 food/water vendors /annually | Municipal wide. | 420 | No. of food vendors screened | * | * | * | * |  |  | ✓ |  |  |  | 6,000.00 |  | CAD (EHU) | MA,MDH,Food /water vendors |
|  |  | 98 | Intensify door to door refuse collection and disposal in urban areas to 60tones | Goaso/Mim | 57.4 tones | Door to door refuse collection increased | * | * | * | * |  |  | ✓ |  |  | 50,000.00 | 50,000.00 |  | CAD (EHU) | Zoomlion,traditional authorities, individual household, private sector |
|  |  | 99 | Increase daily collection and disposal of solid waste in the urban areas to 16,000 tones | Mim/Goaso | 15,840.26 tones | Dialy collection of solid waste increased in urban areas | * | * | * | * |  |  | ✓ |  | 150,000.00 |  |  |  | CAD (EHU) | MHU,EPA,Zoomlion,PPD,traditional authorities, communities |
|  |  | 100 | Erect 30No. Signages and update SNPAS database | Mim/Goaso | No of signaEYS Dept erected and SNPAS updated | -Increased Internally Generated Revenue through easy identification of properties and billing. –Effective response to emergency situations | * | * | * | * |  |  | ✓ |  |  |  |  | 85,428.56(UDG) | PPD | CAD, Fin Dept, Works Dept |
|  |  | 101 | Evacuation of refuse dump | Mim Zongo | - | Refuse dump evecuated | * | * | * | * |  |  | ✓ |  |  |  | 199,420.00 |  | CAD ( EHU) | Zoomlion, MDH,MDE,Traditionalauthorities,communities, |
| Focus Area : NADMO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 102 | Update Climate Change and Disaster Risk Management Plan | Goaso | - | Climate Change and Disaster Risk Management Plan | * | * | * | * | ✓ |  |  |  |  |  |  | 10,000 (UDG) | NADMO,GNFS/Forestry Division/Dept of Agric | CAD, Fin. Dept, NCCE |
| Enviromental Management | Disaster Prevention and management | 103 | Anti-Bush fire Campaigns | Municipal wide | 1 M&E conducted | Communities educated and sensitized | * |  |  |  |  |  | ✓ |  | 1,600.00 |  | 500.00 | 15,000 (UDG) | NADMO,GNFS/Forestry Division/ Dept of Agric | NCCE CAD, Fin Dept |
|  |  | 104 | Monitoring of Anti-Bushfire and Scooping Activities | Municipal wide |  | No. of Communities monitored | * |  |  |  |  |  | ✓ |  | 2,000.00 |  | 600.00 | 20,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 105 | Public education on rainstorms, flooding, and inspection of buildings on areas liable to flooding | Municipal Wide |  | No. of Communities educated on flooding, rainstorms | * |  |  |  |  |  | ✓ |  | 1,200.00 |  | 300.00 | 15,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 106 | Training of staff on climate change & disaster risk reduction, hazard mapping and first aid | Goaso |  | Sixteen(16) staff members trained |  | * |  |  |  |  | ✓ |  | 1,500.00 |  | 500.00 | 30,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 107 | Sensitization on effects of climate change on agriculture | Municipal Wide |  | Thirty five (35) communities sensitized |  | * |  |  |  |  | ✓ |  | 2,000.00 |  | 400.00 | 15,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 108 | Education on effects of emission of carbon monoxide from vehicles and other industrial machines | Municipal Wide |  | Communities, drivers and factory workers educated |  | * |  |  |  |  | ✓ |  | 2,800.00 |  | 400.00 | 5,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 109 | Sensitization program on biodiversity and ecosystem | Municipal wide | 1 M&E conducted | Communities sensitized |  |  | * |  |  |  | ✓ |  | 3,000.00 |  | 700.00 | 10,000 (UDG) | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |
|  |  | 110 | Tree planting on public institutional lands and river banks | Municipal wide |  | 5,000 trees planted |  |  | * |  |  |  | ✓ |  | 2,000.00 |  | 400.00 | 70,000 (UDG) | NADMO | ♦ANMA |
|  |  | 111 | Training and monitoring activities of DVGs | Municipal Wide |  | Seven DVGs trained and monitored |  |  | * |  |  |  | ✓ |  | 500.00 |  | 200.00 | 30,000 (UDG) | NADMO | ♦Forestry Com. MA |
|  |  | 112 | Community durbar on Bushfires | Goaso |  | 260 stakeholders educated |  |  |  | * |  |  | ✓ |  | 2,200.00 |  | 500.00 | 5,000 (UDG) | NADMO | ♦Forestry Com. MA |
|  |  | 113 | Educating and sensitizing saw millers and artisans on safety precautions and other occupational hazards | Municipal Wide |  | 80% of the saw millers and artisans educated |  |  |  | * |  |  | ✓ |  | 2,000.00 |  | 400.00 |  | NADMO | ♦Forestry Com. MA |
|  |  | 114 | Education on bushfires and other harmattan related disasters as well as road and accidents. | Municipal Wide |  | communities educated |  |  |  | * |  |  | ✓ |  | 2,800.00 |  | 600.00 |  | NADMO | ♦Forestry Com. MA |
| Focus Area: Physical/Spatial Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment , Infrastructure, and Human Settlement | Physical/Spatial Planning | 115 | Produce Local Plans for new areas | Abebrese and Dechem | 2 | Number of local plans for new areas produced | * | * | * |  |  |  | ✓ |  | 7,000.00 |  | 4,800.00 |  | M.A PPD | MSPC Members Traditional Authorities |
|  |  | 116 | Support activities of property valuation and revaluation | Municipal Wide | 3 | activities of property valuation and revaluation supported | * | * | * |  |  |  | ✓ |  | 5,000.00 |  | 4,000.00 |  | M.A PPD | MSPC Members Traditional Authorities |
|  |  | 117 | Retracing & scanning of worn-out Local Scheme | Goaso sector 1, Goaso Sector 1 Ext. and Goaso Sector 4 | 3 | Availability of traced and scanned map | * | * |  |  |  |  | ✓ |  | 1,350.00 |  | - |  | PPD | MSPC Members Traditional Authorities |
|  |  | 118 | Prepare 20-year Municipal Spatial Development Framework(SDF) and Structure Plans for Goaso and Mim | Goaso and Mim | - | Number of municipal spatial development framework and structure plan prepared | * | * | * | * | ✓ |  |  |  |  |  |  | 222,857.2 (UDG) | PPD | CAD |
|  |  | 119 | Organize monthly Statutory Planning Committee meeting (Technical Subcommittee and Municipal Spatial Planning Committee) | Municipal Assembly Conference Hall | 24 | All monthly meetings organized | * | * | * | * |  |  | ✓ |  |  |  | 38,400.14 |  | M.A PPD | TSC/MSPC Members |
|  |  | 120 | Sensitize the general public (T.A on Physical Planning related issues) | Municipal wide | 5 | Sensitization programme held No. of outreach sensitization held | * | * | * | * |  |  | ✓ |  | 2,800.00 |  | 500.00 |  | PPD | M.A FM Station Dechem Traditional Council Fawohoyeden Community |
| Focus Area: Public Works, Rural Housing and Water Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment , Infrastructure, and Human Settlement | Infrastructure delivery and Management | 121 | Drilling and Mechanization of boreholes in some communities within the Municipality | Municipal wide |  | Number of boreholes in some communities drilled and mechanized | * | * | * | * | ✓ |  |  |  | 100,000.00 |  |  |  | Works Dept | CAD |
|  |  | 122 | Complete construction of 8- unit kitchen facility for Ghana Police Service | Goaso |  | Kitchen facility constructed for Ghana police service | * | * | * | * |  |  | ✓ |  | 10,000.05 |  |  |  | Works Dept | CAD,GPS |
|  |  | 123 | Complete Drilling of 3 No. boreholes and mechanization of 2 No. boreholes with construction of 2 No. platforms and installation of 2 No. poly tanks (3000 Litres) each and construction of 2 No. concrete pads with installation of 2 No. hand pumps | Dotom CHPS common, Bediako health center, Tachimantia and Gyidim |  | 3 No. boreholes and mechanization of 2 No. boreholes with construction of 2 No. platforms and installation of 2 No. poly tanks (3000 Litr es) each and construction of 2 No. concrete pads with installation of 2 No. hand pumps completed | * | * | * | * |  |  | ✓ |  |  | 50,000.29 |  |  | Works Dept | CAD |
|  |  | 124 | Complete extension of electricity with procision of 60 No. 8M, and 9M and 11M wooden low tension poles, installation of 1 No. 50kws (34/0.433kv) transformer with 50mm and 120mm Aluminum Bare Conductor to cover a distance of 20Km at | Adututu and Nkoranza |  | extension of electricity with procision of 60 No. 8M, and 9M and 11M wooden low tension poles, installation of 1 No. 50kws (34/0.433kv) transformer with 50mm and 120mm Aluminum Bare Conductor to cover a distance of 20Km completed | * | * | * | * |  |  | ✓ |  |  | 196,780.00 |  |  | Works Dept | CAD |
|  |  | 125 | Complete extension of Electricity with provision of 200 No. 8mm and 9m Low TPs, installation of 8 No. 50kws Transformer with 50mm and 120mm Aluminum Bare Conductor at | Kobro, Kofimirekrom, Mireku, Peterkrom, Suntreso, Boakye, Ogyam, and Ohianimguase |  | extension of Electricity with provision of 200 No. 8mm and 9m Low TPs, installation of 8 No. 50kws Transformer with 50mm and 120mm Aluminum Bare Conductor completed | * | * | * | * |  |  | ✓ |  |  | 91,140.60 |  |  | Works Dept | CAD |
|  |  | 126 | Extension of Electricity (Streetlight) with Provision of 80No.8M & 9M Low Tension Poles, installation of 50mm Aluminum Bare Conductor to Cover an Area of (15km) and Installation of 80No. Complete Luminous Bulbs. | Abotanso | - | Number of streetlights installed | * | * | * | * | ✓ |  |  |  | 2,852,936.5(UDG) |  |  |  | MA | Wks Dept, Urban Roads,NADMO, GNFS,EPA, Consultants, RCC |
|  |  | 127 | Support Community initiated projects (Self Help Projects) | District wide |  | No. of community initiated projects supported | * | * | * | * |  |  | ✓ |  |  | 240,563.24 |  |  | CAD | Fin Dept, Works Dept |
|  |  | 128 | Complete payment for the drilling and mechanization of borehole with 10,000 litres capacity polytank at the District Magistrate’s bungalow | Goaso |  | drilling and mechanization of borehole with 10,000 litres capacity polytank at the District Magistrate’s bungalow completed | * | * | * | * |  |  | ✓ |  | 18,042.00 |  |  |  | Works Dept | CAD |
|  |  | 129 | Complete payment for the drilling and mechanization of borehole with 10,000 litres capacity polytank for Fawohpyeden police station | Goaso |  | drilling and mechanization of borehole with 10,000 litres capacity polytank for Fawohpyeden police completed | * | * | * | * |  |  | ✓ |  | 10,041.00 |  |  |  | Works Dept | CAD |
|  |  | 130 | Rehabilitation of Urban Council Office at Mim | Mim | - | Level of rehabilitation of Urban Council Office | * | * | * | * |  |  | ✓ |  | 200,000.00 |  |  |  | Works Dept | CAD |
|  |  | 131 | Repairs and Maintenance of existing water facilities in the Municipality | Municipal wide | No. of existing water facilities repaired/maintained last year | No. of water facilities in the repaired and maintained | * | * | * | * |  |  | ✓ |  | 40,000.00 |  |  |  | Works Dept | CAD |
|  |  | 132 | Maintenance of street lights in the Municipality | Municipal wide | No. of existing water facilities repaired/maintained last year | No. of street lights in maintained | * | * | * | * |  |  | ✓ |  | 200,000.00 |  |  |  | Works Dept | CAD |
|  |  | 133 | Renovation of assembly hall | Goaso |  | Level of renovation | * | * | * | * |  |  | ✓ |  | 285,110.70 |  |  |  | Works Dept | CAD |
|  |  | 134 | Maintenance and repairs of residential and office accommodation | Goaso |  | No. and level of repairs and maintenance of residential and office accommodation | * | * | * | * |  |  | ✓ |  | 60,000.00 |  |  |  | Works Dept | CAD |
|  |  | 135 | Complete extension and re-moulding of administration block | Goaso |  | Level of work done executed on Administration block | * | * | * | * |  |  | ✓ |  | 257,547.65 |  |  |  | Works Dept | CAD |
| Environment , Infrastructure, and Human Settlement | Road and Transport Services | 136 | Organize quarterly Radio sensitization programmes on proper traffic regulation in the Municipality | Municipal Wide | 4 | No of radio sensization programmes organized | * | * | * | * |  |  | ✓ |  |  |  | 2,000.00 |  | CAD (Transport Dep’t) | NRSA |
|  |  | 137 | Maintenance and purchase of fuel and lubricants for official vehicles (6.) and Motor Bikes (7) | Goaso | 6 vehicles and 7motor bikes maintained And provided with fuel | Number of vehicles and Motor bikes maintained /Amount of fuel purchased | * | * | * | * |  |  | ✓ |  |  | 20,000 | 355,500.00 |  | CAD (Transport Dept) | Finance Dept |
|  |  | 138 | Inspection of Lorry terminals | Municipal Wide | 5 Terminals inspected | Number of terminals upgraded and inspected | * | * | * | * |  |  | ✓ |  |  |  | 1,500.00 |  | CAD (Transport Dept) | Works Dept, NRSA, Fire Serv. |
|  |  | 139 | Maintenance of roads within the Municipality | Municipal wide |  | Number of vehicles and motorbikes insured | * | * | * | * |  |  | ✓ |  |  |  | 170,000.00 |  | CAD (Transport Dept) | Works Dept |
|  |  | 140 | Insure MA vehicles and motor bikes | Goaso | Vehicles insured | Number of vehicles and motorbikes insured | * | * | * | * |  |  | ✓ |  |  |  | 30,000.00 |  | CAD (Transport Dept) | Works Dept |
|  |  | 141 | Update and map-out basic services (roads, pedestrian walkways, streets, drainage, electricity/streetlights, solid waste/ Sanitation, water) in urban areas | Municipal wide |  | basic services (roads, pedestrian walkways, streets, drainage, electricity/streetlights, solid waste/ Sanitation, water) in urban areas updated | * | * | * | * | ✓ |  |  |  |  |  |  | 37,142.86(UDG) | CAD (transport dept) | Works, EHU, physical planning |
| Thematic Area/Development Dimension: Governance, Corruption and Public Accountability u |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Finance and Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance and Audit | 141 | Conduct monthly Audit on Payroll Management Reviews, Cash and Revenue Management, Asset Management, Transport Manageme n, Procurement /Stores Management) | Goaso | 1 no.Cash and Revenue ,Asset Management, Transport Management,ProcurementManagement Audit Conducted | No. of monthly audits conducted No. of management areas audited | * | * | * | * |  |  |  | ✓ |  |  | 4,250.00 | 1,200.00 | CAD (IAU) | MOFA, Finance, Revenue, Estate Officer and Stores, Transport Unit, Procurement Unit |
|  |  | 142 | Attend Capacity Building programmes | Goaso and Out of Goaso | 2 Capacity Building Programs attended | No. of Capacity building Programs attended | * | * | * | * |  |  |  | ✓ |  | 6,000.00 | 3,500.00 | 800.00 | CAD (IAU) | GIZ, IAA, LGS |
|  |  | 143 | Purchase value books | Goaso | 4 | No. of Value books purchased | * | * | * | * |  |  |  | ✓ | 2,000 |  |  |  | Finance department | Central Administration |
|  |  | 144 | Renovation /furnishing of selected revenue offices & erection of Kiosk at revenue check points | Municipal wide | 4 | No of renovations conducted | * | * | * | * |  | ✓ |  |  | 20,000 |  |  |  | Finance department | Central Administration, Works |
|  |  | 145 | Pay ex-gratia of Assembly members | Goaso | - | No. of Assembly Members paid. | * | * | * | * |  |  |  | ✓ |  | 84,000.00 |  |  | Fin.Dept. | Assembly Members |
| Focus Area: General Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 146 | Hold Sub-committee, Executive Committee ,Management Meetings & Assembly meetings | Goaso | 16 | No. of meetings held | * | * | * | * |  |  |  | ✓ |  |  | 118,730.00 |  | CAD (Admi) | Fin. Dept., Assembly Members,Other Depts |
|  |  | 147 | Hold 12 No. heads of departments meetings | Goaso | 4 | No. of HOD meetings held | * | * | * | * |  |  |  | ✓ |  |  | 5,000.00 |  | CAD (Admi) | Other depertments |
|  |  | 148 | Hold 12 No MUSEC meetings | Goaso | 12 | No. of MUSEC meetings held | * | * | * | * |  |  |  | ✓ |  |  | 19,825.00 |  | CAD(Admi) | Security Services (GPS, GNFS, BNI), TAs |
|  |  | 149 | Organize National Days Celebrations (Independence Day, Mayday, Farmers’Day) etc | Municipal wide | 3 | National Days Organised | * | * |  | * |  |  |  | ✓ |  | 111,960.00 | 17,000.00 |  | CAD(Admi) | Other relevant departments |
|  |  | 150 | Support religious festivities (X’mas, Easter, Eidlfitr, Eid Adha, etc.) | Municipal wide | 3 | No. of religious festivities supported | * | * | * | * |  |  |  | ✓ |  | 105,560.00 |  |  | CAD | Religious Groups, Fin. Dept. |
|  |  | 151 | Organize 1 No. capacity building programmes for caterers and selected teachers of the beneficiaries schools of the Ghana School Feeding programme | Goaso | 1 | 1No. of capacity building programme organised |  |  |  | * |  |  |  | ✓ |  |  | 4,050.00 |  | CAD(Admi) | EYS DEPT, Fin. Dept. |
|  |  | 152 | Renew Health Certificates of 41 School Feeding Caterers. | Goaso | 1 | No. of School Feeding Caterers’Health Certificates renewed. |  |  |  | * |  |  |  | ✓ |  |  | 1000.00 |  | CAD (EH) | GHS, Fin. Dept. |
|  |  | 153 | Service contingency activities | Goaso | - | No. of contingency activities serviced | * | * | * | * |  |  |  | ✓ |  | 150,000.00 |  |  | CAD(Admi) | Fin. Dept. |
|  |  | 154 | Build capacity of Zonal Councils | Municipal wide | - | No. of members supported | * | * | * | * |  |  |  | ✓ |  | 15,000.00 |  |  | CAD(Admi) | Zonal/Urban Councils, Fin. Dept. |
|  |  | 155 | Cater for protocol services (hosting of official guests) | Goaso | - | Protocol services provided for | * | * | * | * |  |  |  | ✓ |  |  | 50,600.00 |  | CAD(Admi) | Fin. Dept. |
|  |  | 156 | Pay NALAG dues/contributions | Goaso | - | NALAG dues/contributions paid for | * | * | * | * |  |  |  | ✓ |  |  | 5000.00 |  | CAD(Admi) | Fin. Dept. |
|  |  | 157 | Service office utility bills (Electricity, water, Telecommunication and Postal CharEYS Dept) | Goaso | - | Expenditure on office utilities | * | * | * | * |  |  |  | ✓ |  |  | 26,000.00 |  | CAD(Admi) | Fin. Dept |
|  |  | 158 | Hold 4 No. Audit Committee meetings | Goaso | 4 | No. of Audit Committee meetings organized | * | * | * | * |  |  |  | ✓ |  |  | 20,000.00 |  | CAD(Audit Unit) | Fin. Dept. |
|  |  | 159 | Organize town hall meetings/forum and MCE visits to communities to promote Social Accountability/Public Education and Sensitization | Municipal Wide | 4 | No. of communities visited and Town hall meeting, MCE visits Organised | * | * | * | * |  |  |  | ✓ |  |  | 20,000.00 |  | CAD(Admi) | Fin. Dept. |
|  |  | 160 | Provision of enough office space for Records Unit | Goaso | - | To enhance effective service delivery standards in archives mgt. |  | * |  |  |  | ✓ |  |  |  |  | 8,000 |  | CAD (RMU) | procurement &PRAAD |
| Focus Area: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Administration and management | Human Recourse Management | 161 | Organise Capacity Building Trainings on Local Government Protocols, Procurement Audit, Revenue Mobilization, I.T Systems, Agric, E- Records & file management, semi current records &Prosecution& Inspection | Goaso | 2 | No. of Trainings Organised | * | * | * | * |  |  |  | ✓ |  | 7,000.00 | 14,000.00 | 6,600.00 | HRD | CAD, Fin. Dept., EHU, Revenue Database, Procurement, Dept of Agric |
|  |  | 162 | Submit quarterly reports | Goaso | 4 | Reports Submitted | * | * | * | * |  |  |  | ✓ |  |  | 200 |  | HRD | CAD, Fin. Dept. |
|  |  | 163 | Validate monthly salaries | Goaso | 12 | Salaries Validated | * | * | * | * |  |  |  | ✓ |  |  | 600 |  | CAD (HRD) | Fin. Dept. |
|  |  | 164 | Purchase Office Logistics | Goaso | - | Logistics purchased | * | * | * | * |  |  |  | ✓ | 8,000 |  |  |  | Procurement | Fin. Dept.,HRD |
| Focus Area: Statistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Administration and management | Planning, Budgeting, Coordination and Statistics | 165 | Conduct quarterly market reading (CONSUMER PRICE INDEX | Municipal wide | 4 | Number of Market readings conducted | * | * | * | * |  |  |  | ✓ | 2,000 |  |  |  | Statistics Department | Central Administration and GSS |
|  |  | 166 | International Comparison Program (ICP) | Municipal wide | 4 | Number of international comparisons conducted | * | * | * | * |  | ✓ |  |  | 2,000 |  |  |  | Statistics Department | Central Administration and GSS |
|  |  | 167 | Update Business Register | Municipal wide | 4 | Number of businesses registered | * | * | * | * |  | ✓ |  |  | 2,000 |  |  |  | Statistics department | Central Administration |
|  |  | 168 | Collection and Dissemination of Administrative data | Municipal wide | 4 | No. of Administrative data diseminated | * | * | * | * |  |  |  | ✓ | 2,000 |  |  |  | Statistics department | Central Administration and GSS |

| Thematic Area/Development Dimension: Implementation, Co-ordination, Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Focus Area: Planning, Budgeting, Coordination and Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Planning, Budgeting, Coordination and Statistics | 169 | Coordinate implementation of 2023 CAAP and thematic plans (UDAP-2022-23, WASH, NACAP, RIAP, LED Plan, GovID, PPS,MESSAP) | Goaso | 4 | No of plans coordinate d and implemented | * | * | * | * |  | ✓ |  | 20,000.00 | 30,000.00 | 20,000.00 | CAD(Planning Unit) | Other Depts,NGOs/CSOs, IRC, MLGDRD, LGS, RCC |
|  |  | 170 | Hold 4 quarterly MPCU meetings, 3 Planning sessions | Goaso | 3 | 3 No. MPCU meeting organied | * | * | * | * | ✓ |  |  |  | 7,000.00 |  | CAD(Planning Unit) | Other Depts,NGOs/CSOs, IRC, LGS |
|  |  | 171 | Monitor and Evaluate programmes and projects, Conduct safeguards, and Review implementation 2023 CAAP | Goaso | 3 | No. of projects and programs monitored and review of the CAAP conducted | * | * | * | * |  | ✓ |  | 10,000.00 | 20,000.00 | 314,352.72.00 (UDG) | CAD (Planning Unit) | Other Depts,NGOs/CSOs, MLGDRD, IRC |
|  |  | 172 | Organize quarterly Budget committee meetings | Goaso | 3 | No. of quarterly budget committee meetings conducted | * | * | * | * |  | ✓ |  |  | 10,000 |  | CAD(Budget ) | Other Depts,NGOs/CSOs |
|  |  | 173 | Organise quarterly review meetings of Procurement plan | Goaso | 1 | Conducts reviews | * | * | * | * |  | ✓ | 2,000 |  |  |  | CAD( Planning Unit) | Other Depts,NGOs/CSOs |
|  |  | 174 | Procure 6No. Laptop computers, 12No. Desktop computers, 3No. Photocopiers, 2No.GPS,6No. Printers, 1No. Projector and screen, 2No. File Cabinets, 5No.Comb-binding machines, 5No. Giant stale machines, 2NO. Internet Rioters, office furniture | Goaso | - | Number of laptop computers, desktop computers, photocopier, GPS, printer, projector procured | * | * | * | * | ✓ |  |  |  |  | 179,214.26 (UDG) | CAD (Procurement Unit) | Fin.Dept., IT, planning Unit |
|  |  | 175 | Organize training for MPCU members in Urban Planning and management for Monitoring and Evaluation, and Environmental, Social and Project Impact Assessment | Goaso | - | Number of trainings for MPCU members in urban planning and management organized | * | * | * | * | ✓ |  |  |  |  | 74,285.7 (UDG) | CAD Planning Unit) | Other Depts,MPCU MEMBERSNGOs/CSOs, IRC, RCC |
|  |  | 176 | Organize training for Revenue Technical Working Group /Team and Finance staff in modern revenue management, Application of Excel in Automating bank Reconciliation, Tax Applications, Pay slip for non-mechanized staff | Goaso | - | Number of training for revenue technical working Group organized | * | * | * | * | ✓ |  |  |  |  | 55,714.28 (UDG) | CAD Planning Unit) | Other Depts,NGOs/CSOs, , RCC |
|  |  | 177 | Valuation of Properties | Goaso | - | No. of valuation conducted | * | * | * | * | ✓ |  |  |  |  | 74,285.72(UDG) | CAD (Planning Unit) | Other Depts,NGOs/CSOs, |
|  |  | 178 | Conduct Mid-Term Review of 2022-2025 MTDP | Goaso | - | Improved plan implementation and service delivery | * | * | * | * | ✓ |  |  |  |  | 37,142.85 (UDG) | CAD (Planning Unit) | Other Depts,NGOs/CSOs, MLGDRD, IRC |