DRAFT COMPOSITE ANNUAL ACTION PLAN- 2024

| Programme Area (PBB) | Sub-Programme(PBB) | No. | Broad Activities | Location | Baseline | Output Indicators | Quarterly Time schedule |  |  |  | Programme status |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 1st | 2nd | 3rd | 4th | New |  | Ongoing |  | GoG | DACF | IGF | Donor | Lead | Collaborating |  |
| Thematic Area/Development Dimension: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Agricultural Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Services and management Agricultural Services and management | 1 | Service operational activities (utilities, office consumables, fuel and; insurance and road worthy) | Goaso | No. of utilities and consumables purchased | No. of utilities and consumables purchased | * | * | * | * |  |  | ✓ |  | 4,000 | 150,000 | 10,000 |  | Dept. of Agric. | Fin Dept., CAD, CIDA |  |
|  |  | 2 | Establishment 60 of field demonstrations | Municipal Wide | 14 maize, 14 rice and 14 vegetable demostrations were establised | Number of maize, Rice and Vegetables demonstration fields established | * | * | * | * |  |  | ✓ |  | 1,000 |  | 700 |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
|  |  | 3 | Organize farmer based trainings | Municipal Wide | 4 farmer trainings were conducted | No. of farmer based trainings were conducted |  | * | * | * |  |  | ✓ |  | 1,500 |  | 600 |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
|  |  | 4 | Organize 2 RELC planning session | Municipal Wide | 2 | RELC planning Sessions conducted | * | * | * | * |  |  | ✓ |  | 2,000 |  | 1,300 |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
|  |  | 5 | Conduct 2 survey activities | Municipal Wide | 2 surveys conducted | surveys conducted |  | * | * |  |  |  | ✓ |  | 1,000 |  | 500 |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
|  |  | 6 | Organise staff meetings | Goaso | 4 | No. of staff meetings conducted | * | * | * | * |  |  | ✓ |  | 1,500 |  | 700 |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
|  |  | 7 | MP Support to Farmer Group and Traders | Municipal Wide |  | Farmer groups and traders supports by MP | * | * | * | * |  |  | ✓ |  |  | 56,000.00 |  |  | Dept. of Agric. | Fin Dept, CAD, CIDA |  |
| Focus Area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development Economic Development | Trade, tourism and industrial development Trade, tourism and industrial development | 8 | Build capacities of MSMEs (no) through technical and management training, NVTI exams and apprentices training | Municipal Wide | 8 | No. of technical training conducted No. of Management training conducted | * | * | * | * |  |  | ✓ |  | 7,000.00 |  |  | 8,000 | BAC | CAD, Fin Dept, NBSSI, GRATIS, |  |
|  |  | 9 | Build capacity of MSMEs in Financial Management and access to financial support | District wide | 4 | No. of financial management training conducted/No. of MSMEs accessed financial support | * | * | * | * |  |  | ✓ |  |  | 2,00 |  | 6,000.00 | BAC | CAD, Fin Dept, NBSSI, GRATIS, |  |
|  |  | 10 | Construction of 1No. 2-2storey 28-unit lockable stores, 1No. 40-unit lockable stores, 1No. Meat shop, 1No. Security post and 1No. Fire hydrant | Abotanso |  | % of construction works carried out | * | * | * | * |  |  | ✓ |  |  |  |  | 3,876,000.00(UDG) | BAC | CAD, Wks Dept, Market Women, Traditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |  |
|  |  | 11 | Construction of 1No. 28-unit lockable stores, 1No. Security post, 1No. Sanitary block , 2No. Skip containers and waste bins, 8No. 14-unit open Market Stalls, 1No. Creche ,1No. Mechanised borehole, water storage facility. | Abotanso |  | % of construction works carried out | * | * | * | * |  |  | ✓ |  |  |  |  | 2,971,000.00(UDG) | BAC | CAD, Wks Dept, Market Women, Traditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |  |
| Economic Development | Trade, tourism and industrial development | 12 | Improvement of access road, market and, lighting Fencing, 1No. Mechanised borehole, water storage facility, Paving of market spaces | Abotanso |  | Roads, market, lightening and fencing improved, borehole mechanised and market spaces paved | * | * | * | * |  |  | ✓ |  |  |  |  | 1,719,000.00(UDG) | MA | Wks Dept, Market Women, Traditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |  |
|  |  | 13 | Hold 6No. LED fora with local private sector community/businesses on strategies to promote business development and economic growth | Goaso/Mim, Akrodie,Kasapin,Ayomso,Fawohoyeden |  | Number of LED with local private sector community conducted | * | * | * | * |  |  | ✓ |  |  | 5,000.00 | 5,000 | 57,678.57 (UDG) | BAC | CAD, Fin Dept, NBSSI, GRATIS, |  |
|  |  | 14 | Review, prepare and update Annual business support action plan | Goaso |  | Number of annual business support action plan reviewed and prepared | * | * | * | * |  |  | ✓ |  |  |  |  | 43,714.29 (UDG) | BAC | CAD , NBSSI |  |
| Focus Area: Industrial Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development | 15 | Provide training for apprentices towards NVTI and NABPTEX Certification | Goaso | 100 | 100 apprentices trained for NVTI and NABPTEX certification | * | * | * | * |  |  | ✓ |  |  |  |  | 21,000.00 | TSC | CAD, Fin Dept, BAC, |  |
|  |  | 16 | Provide practical knowledge through industrial attachment for students from the University/Polytechnic or technical institution | Goaso | 5 | Number of students from the Universities and Polotechnics trained | * | * | * | * |  |  | ✓ |  |  |  |  | 1,000.00 | TSC | CAD, Fin Dept, BAC, |  |
| Economic Development | Trade, tourism and industrial development | 17 | Carry out tracer study update for apprentices who graduated in the last three years(2020,2021,2022) | Goaso | 70 | Number of past apprentices contacted | * | * | * | * |  |  | ✓ |  |  | 2,000.00 |  |  | TSC | CAD, Fin Dept, BAC, |  |
|  | Trade, tourism and industrial development | 18 | Performance measurement for all staff in center | Goaso | 19 | Number of staff whose performance has been assessed | * | * | * | * |  |  | ✓ |  | 500 |  |  |  | TSC | CAD, Fin Dept, BAC, |  |
|  |  | 19 | Identify training needs of staff and train them | Goaso | 4 | Number of staff trained | * | * | * | * |  |  | ✓ |  |  |  | 2,500 |  | TSC | CAD, Fin Dept, BAC, |  |
|  |  | 20 | Organise sensitization on radio/FM about Technology Solution Centre | Municipal wide |  | Number of sensitization programmes organised | * | * | * | * |  |  | ✓ |  |  | 2,000 |  |  | TSC | CAD, Fin Dept, BAC,,FM stations |  |
| Thematic Area/Development Dimension: Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery Social Services Delivery Social Services Delivery | Social Welfare and Community Development | 21 | Supervision of 5 juvenile placed under trained probationers | 5 selected probation communities | 5 Juvenile placed under trained probationers | Number of juveniles supervised under court of law | * | * | * | * |  |  | ✓ |  | 1,000.00 |  |  | 3,000.00 | DSWCD | Family Tribunal Court, Ghana Police Service, GES |  |
|  |  | 22 | Conduct Investigations and submit Social Enquiry Reports to the Juvenile Court | Goaso | 5 Social Enquiry Report submitted to the Juvenile Court | Number of staff/agents trained on probation issues | * | * | * | * |  |  | ✓ |  | 1,000.00 |  |  | 4,000.00 | DSWCD | Family Tribunal Court, GES, Ghana Police Service |  |
|  |  | 23 | Organize Refresher training course on Child Protection and its related Cases for 10 committees | Duase, Asukese,Bedabour, Donimase, Akrodie Manhyia,Kasapin, Asumura, Mfama, Mfante | 7 communities | No. of CCPC members trained | * | * | * | * |  |  | ✓ |  | 3,000.00 |  |  | 2,000.00 | DSWCD | MA, CSO, Community Opinion Leaders Ghana Police, GES. |  |
|  |  | 24 | Reconcile 150 Family related issues | Goaso | 135 Family related issues | Number of family related issues reconciled | * | * | * | * |  |  | ✓ |  |  |  |  | 2,000.00 | DSWCD | CAD, CSO’s, Ghana Police, GES, |  |
|  |  | 25 | Sensitize 5 Rural & settler communities on Effect of Early Child Marriage & Teenage Pregnancy | Bediako, Tipokrom, Diasibey, Pomaakrom, Alhassan Gruma Akura | 5 | No. of Rural & settler communities sensitized on Effect of Early Child Marriage & Teenage Pregnancy | * | * | * | * |  |  | ✓ |  | 3,500.00 |  |  | 1,000.00 | DSWCD | CAD, CHRAJ, Legal Aid, CSO’s. DOVVSU |  |
|  |  | 26 | Hold 3No. radio discussions and 5No community durbars on the Children’s Act 1998 (ACT 560 | Goaso & Manukrom No.1, Gyaenkontabuo, Ayomso, Ampenkro, Mpamase | 6 | Number of Public Educations carried Out | * | * | * | * |  |  | ✓ |  | 1,500.00 |  |  | 4,000.00 | DSWCD | CAD, CSO’s GES, Community Opinion Leaders |  |
|  |  | Focus Area :Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 27 | Update Data on Vulnerable (Persons with Disability (PWD’s) within the Municipality | 8 Zonal council | 40 PWD’s were updated within the Municipality | Number of PWD’s registered | * | * | * | * |  |  | ✓ |  | 1,500.00 |  |  |  | DSWCD | CAD,, PWD’s Zonal Representatives |  |
|  |  | 28 | Monitor & Supervise 44 LEAP Communities and it’s Pay-point Centres | 44 LEAP communities | Routinely cycle payment on 44 communities | Number of Beneficiaries Paid & Monitored | * | * | * | * |  |  | ✓ |  | 1,000.00 |  |  | 1,500.00 | DSWCD | LEAP PFI, Ghana Police Service, CLICs/LEAP Focal Persons |  |
|  |  | 29 | Livelihood Empowerment Training for Selected Groups of PWD’s on Liquid Soap Making | 20 selected PWD groups | 20 PWD’s were trained in Liquid soap making | Number of PWD’s Empowered | * | * | * | * |  |  | ✓ |  | 4,000.00 |  |  |  | DSWCD | CAD, Fin. Dept, PWD’s Zonal Reps, BAC |  |
|  |  | Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 30 | Organize community dialogues and durbars to sensitize vulnerable women on Land Rights | Tweapease, Peterkrom, Kyenkyehene, Fawohoyeden, Adiepena, Aworokese, Asuadei, Nkrankrom, Anwiawia,Driverkrom | 4 | No. of community dialogues and durbars organized for vulnerable women on Land RightsCommunity dialogues organised | * | * | * | * |  |  | ✓ |  | 2,500.00 |  |  | 3,500.00 | DSWCD | CHRAJ, Community Opinion Leaders, CSO’s, Legal Aid |  |
|  |  | 31 | Provision of Social Protection Services to the vulnerable (registration/Renewal of NHIS cards to LEAP and PWDs beneficiaries) | Mensakrom, OhiayeyaAsukese, Akwaduro,Fianko, Kwaoprete Dottom | Number of registration done | Services provided | * | * | * | * |  |  | ✓ |  | 2,000.00 |  |  | 3,500.00 | DSWCD | NCCE, Community Opinion Leaders, CSO’s, CAD, |  |
|  |  | 32 | Build capacity of persons with disability to be able to report perpetrators of discrimination and stigmatization | Goaso | 3 | Number of training organised | * | * | * | * |  |  | ✓ |  | 3,500.00 |  |  | 5,500.00 | DSWCD | NCCE, CSO’s, CAD,, DOVVSU |  |
|  |  | 33 | Hold MGCPC Meetings | Goaso | 2 | Number of meetings held | * | * | * | * |  |  | ✓ |  |  |  |  | 6,000 | DSWCD | MGCPC Members |  |
| Focus Area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery Social Services Delivery | Education, Youth and Sports Services Education, Youth and Sports Services | 34 | Complete construction of 5 No. 3-unit classroom block, staff common room, store, 4-seater aqua privy toilet and provision of furniture | Anyinmaye M/A primary school, Ampenkro-Koforidua, Ampenkro, Bediako, , Gyasikrom, |  | No. of classroom blocks completed and furnished | * | * | * | * |  |  | ✓ |  |  | 3,953,121.48 |  |  | GES | CAD, Works Dept |  |
|  |  | 35 | Complete construction of 1 No. 6 unit classroom block with suspended ground floor slap | Mim SHS | 75% | Level of construction of Classroom block | * | * | * | * |  |  | ✓ |  |  | 250,617.78 |  |  | GES | CAD,Works dept |  |
|  |  | 36 | Complete Construction of 1No. 3-Unit Classroom Block with Staff Common, Headmaster’s office, store and Provision of 90No. Dual Desk at Ahafoman JHS | Goaso |  | Classroom block completed | * | * | * | * |  |  | ✓ |  |  |  |  | 93,887.00 | Works Dept | CAD,Goaso Zonal Council, GES |  |
|  |  | 37 | Complete Construction of 1no. 3-unit classroom block with staff common room, headmaster’s office, store and provision of 90No. Dual Desk at Fawohoyeden | Fawohoyeden |  | Classroom block completed | * | * | * | * |  |  | ✓ |  |  |  |  | 58,020.02 | Works Dept | MA,Ayomso Zonal Council,GES |  |
|  |  | 38 | Construction of 1No. 3unit Classroom BLK | Dechem |  | Classroom block constructed | * | * | * | * | ✓ |  |  |  |  | 420,000.00 |  |  | Works Dept | MA,Ayomso Zonal Council,GES |  |
|  |  | 39 | Construction of 1No. 6 Unit Classroom with ancillary facility | Mim MA Primary |  | Classroom block constructed | * | * | * | * | ✓ |  |  |  |  | 582,827.52 |  |  | Works Dept | MA,Ayomso Zonal Council,GES |  |
|  |  | 40 | Organize common test in literacy and numeracy for primary two and four children. | Municipal Wide |  | common test in literacy and numeracy for primary four and six children organized |  |  |  | * |  |  | ✓ |  |  | 10,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 41 | Organize capacity-building workshop for teachers in ICT, Asante Twi and core subjects | Goaso | 1 | Number of capacity-building workshop for teachers in ICT and core subjects organized |  | * |  |  |  |  | ✓ |  |  | 20,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 42 | Organize Science, Technology, Mathematics and Innovative Education (STMIE) clinic | Municipal Wide | 1 | Number of Science, Technology, Mathematics and Innovative Education (STMIE) clinic organized |  | * |  |  |  |  | ✓ |  |  | 25,000.00 |  |  | GES | CAD, Fin Dept, Works Dept |  |
|  |  | 43 | Organize Best teacher and worker awards for deserving teachers/workers | Goaso |  | Best teacher and worker awards for deserving teachers/workers organized |  |  | * |  |  |  | ✓ |  |  | 50,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 44 | Conduct regular monitoring & supervision in all public basic schools | Municipal Wide |  | No. of monitoring/supervisions conducted. No. of public basic schools monitored/supervised | * | * | * | * |  |  | ✓ |  | 30,000 | 10,000 | 5,000 |  | GES | CAD, Fin Dept, |  |
|  |  | 45 | Conduct regular payroll audit in all schools | Municipal Wide |  | Number of regular payroll audit in all schools conducted |  |  | * |  |  |  | ✓ |  |  | 10,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 46 | Conduct comprehensive inspection of school and issue report | Municipal Wide |  | Number of comprehensive inspection of school conducted and report issued | * | * | * | * |  |  | ✓ |  |  | 30,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 47 | Organize school level SPAM/durbar in all schools | Municipal Wide |  | School level SPAM/durbar organized in all schools |  |  |  | * |  |  | ✓ |  |  | 8,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 48 | Organize workshop for DEO staff and headteachers on financial and administrative practices to strengthen accountability and transparency | Municipal Wide |  | Number of workshops for DEO staff and headteachers on financial and administrative practices to strengthen accountability and transparency organized |  |  | * |  |  |  | ✓ |  |  | 5,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 49 | Provide schools with essential supplies - (TLMs) markers, cardboard supplementary readers etc | Municipal Wide |  | Number of teaching learning materials provided for schools | * |  |  |  | ✓ |  |  |  |  | 5,000.00 | 10,000 |  | GES | CAD, Fin Dept, |  |
|  |  | 50 | Conduct reading competition at the public basic schools and Mock exams for JHS 3 students | Municipal Wide | 1 | Reading competition at the public basic schools conducted |  | * |  |  |  |  | ✓ |  |  | 50,000.00 | 10,000 |  | GES | CAD, Fin Dept, |  |
|  |  | 51 | Organize regular radio discussions on best practices in student assessment to build up student confidence and minimize examination malpractices | Municipal Wide | 4 | No. of Radio discussions on best practices in student assessment organized | * | * | * | * |  |  | ✓ |  |  | 5,000 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 52 | Organize my first day at school | Municipal Wide |  | Number of schools visited | * |  |  |  |  |  | ✓ |  | 20,000 | 5,000 | 5,000 | 10,000 | GES | CAD, Fin Dept, |  |
|  |  | 53 | Training of teachers in all GALOP schools (B1 – B3) on the implementation of transition of English plus programme and in service training for all teachers | Municipal Wide | Municipal wide | Number of teachers trained | * | * | * | * |  |  | ✓ |  | 10,000 |  |  | 6,000 | GES | CAD, Fin Dept, |  |
|  |  | 54 | Organization of General Assembly in all schools (teachers, PTA, SMC and other Stakeholders) | Municipal Wide |  | Community meets held | * |  |  |  |  |  | ✓ |  | 6,000 |  |  |  | GES | CAD, Fin Dept, |  |
|  |  | 55 | Organize common test in literacy and numeracy for primary two and four children. (NST) | Municipal Wide |  | common test in literacy and numeracy for primary four and six children organized |  | * |  |  |  |  | ✓ |  | 10,000 |  |  |  | GES | CAD, Fin Dept, |  |
|  |  | 56 | Organize capacity-building workshop for teachers in ICT, Asanti Twi and core subjects | Municipal Wide | 1 | Teachers trained in ICT and core subjects |  |  | * |  |  |  | ✓ |  | 20,000 |  |  |  | GES | CAD, Fin Dept, |  |
|  |  | 57 | Organize Science, Technology, Mathematics and Innovative Education (STMIE) clinic | Municipal Wide | 1 | Science, Technology, Mathematics and Innovative Education (STMIE) clinic organized |  |  |  | * |  |  | ✓ |  |  | 25,000 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 58 | organize orientation for newly trained teachers | Municipal Wide |  | Number of orientation for newly trained teachers organized |  |  |  |  |  |  | ✓ |  | 10,000 |  |  |  | GES | CAD, Fin Dept, |  |
|  |  | 59 | Organize (inter-school sports and athletic competition, cultural competition and municipal and circuit cultural day celebration | Municipal Wide | 1 | Number of inter-school sports and athletic competition and cultural competition organised |  | * |  |  |  |  | ✓ |  |  | 23,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 60 | Support girls by providing a life-skills development programme | Municipal Wide | 1 | Number of girls provided with life-skills development programmes | * | * | * | * |  |  | ✓ |  |  | 8,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 61 | Promote activities of female mentors (Teachers, Community women and older girls) to mentor girls | Municipal Wide |  | Activities of female mentors (Teachers, Community women and older girls) to mentor girls promoted |  |  |  |  |  |  | ✓ |  |  | 5,000.00 |  |  | GES | CAD, Fin Dept, |  |
|  |  | 62 | Support D.E.O. with logistics to assist schools write BECE | Municipal Wide | 1 | No. of logistics provided to D.E.O. to support schools during BECE |  | * |  |  |  |  |  |  |  | 20,000 |  |  | GES | CAD, Fin Dept, |  |
| Social Services Delivery | Education, Youth and Sports Services | 63 | Provide financial assistance to needy but brilliant students | Municipal Wide |  | Financial assistance to needy but brilliant students provided | * | * | * | * |  |  | ✓ |  |  | 86,001.86 |  |  | GES | CAD, Fin Dept, |  |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education, Youth and Sports Services | 64 | Construction of multi –purpose court ( volley ball, Basketball, hand ball) | Goaso | - | Multi-purpose court constructed | * | * | * | * | ✓ |  |  |  |  | 10,000.00 | 10,000.00 | 40,000.00 | NSA | EYS DEPT, GKA, ARVA, ANMA, GTC |  |
|  |  | 65 | Organize May Day Games for workers | Goaso | 1 | May Day Games organized |  | * |  |  |  |  | ✓ |  |  | 1,000.00 | 2,000.00 | 4,000.00 | NSA | ANMA, Media, GTC |  |
|  |  | 66 | Organize keep fit Games | Municipal Wide | 4 | Keep Fit games organized | * | * | * | * |  |  | ✓ |  |  | 5,000.00 | 500.00 | 4,000.00 | NSA | GKA, ANMA, GHS, Media |  |
|  |  | 67 | Supervise Second Division League | Municipal Wide | 20 | Second Division League Organized |  | * | * | * |  |  | ✓ |  |  | 500.00 | 500.00 |  | NSA | ANMA, Media |  |
|  |  | 68 | Host 150 Radio education programs | Municipal Wide | 90 | Radio education programs organized | * | * | * | * |  |  | ✓ |  |  |  |  | 500.00 | NSA | Media |  |
| Focus Area: Culture and National Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Education, Youth and Sports Services | 69 | Support Traditional authorities and development of culture | Municipal Wide |  | Number of traditional authorities supports Number of cultural development activities supported | * | * | * | * | ✓ |  |  |  |  |  |  |  | CAD | Fin Dept, Trad. Auth, CNC |  |
| Focus Area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery Social Service Delivery | Public Health Services and Management Public Health Services and Management | 70 | Support the Municipal HIV/AIDS Committee Response Initiative | Municipal Wide | - | Municipal HIV/AIDS Committee Response Initiative supported | * | * | * | * |  |  | ✓ |  |  |  |  |  | CAD | GHS |  |
|  |  | 71 | Complete construction of Maternity ward at | Asumura | 1 | construction of Maternity ward completed | * | * | * | * |  |  | ✓ |  |  | 71,105.57 |  |  | Works Dept | GHS, Works Dept |  |
|  |  | 72 | Complete construction of 2 No. CHPS compound at | Awewoho Manhyia ,Dotom | 1 | Construction of 2No. CHPS compound completed | * | * | * | * |  |  | ✓ |  |  | 38,236.84 |  |  | Works Dept | GHS, Works Dept |  |
|  |  | 73 | Construction of 2No. CHPS Compound at Kumaho and Aworokrom | Kumaho and Aworokrom |  | CHPS compound constructed | * | * | * | * | ✓ |  |  |  |  | 115,806 |  |  | Works Dept | CAD, Ayomso Zonal Council, GHS |  |
|  |  | 74 | Complete infrastructural projects in the constituency by the Hon. MP | Constituency Wide | - | Infrastructural projects in the constituency completed | * | * | * | * |  |  | ✓ |  |  | 180,000.00 |  |  | CAD | GHS, Works Dept |  |
|  |  | 75 | Support the Municipal Health Directorate to organize Roll Back Malaria Programmes | Municipal Wide | - | No. of Roll Back Malaria Programme supported | * | * | * | * |  |  | ✓ |  |  | 21,500.47 |  |  | CAD | GHS |  |
|  |  | 76 | Complete construction of 1No. 16-seater water closet toilet facility at Mim | Mim |  | construction of 1No. 16-seater water closet completed | * | * | * | * |  |  | ✓ |  |  |  | 258,607.60 |  | Works Dept | CAD, Mim Zonal council, EHU |  |
|  |  | 77 | Support Health Programme (Maternal and Child Health Outreach and National Immunization Programme) | Municipal Wide | - | Health Programme (Maternal and Child Health Outreach and National Immunization Programme) supported | * | * | * | * |  |  | ✓ |  |  | 30,000.00 |  |  | CAD | GHS |  |
|  |  | 78 | Conduct Monthly social and risk communication in the Municipality | Six Sub-district |  | Public Sensitized | * | * | * | * |  |  | ✓ |  | 54,000 |  |  |  | GHS | MEDIA, CAD |  |
|  |  | 79 | Organize school heath service in (20 JHS and 20 Primary School) | Six Sub-district |  | school health activities conducted | * | * | * | * |  |  | ✓ |  | 6000 |  |  |  | GHS | GES,CAD |  |
|  |  | 80 | Increase Education on Family planning acceptor rate | Six Sub-district |  | Create awareness on F/P and provide services on various methods | * | * | * | * |  |  | ✓ |  | 8000 |  |  |  | GHS | MEDIA, CAD |  |
|  |  | 81 | Capacity building of staff for effective service delivery and surveillance activities | Four Sub-districts | 4 | Training and refresher training on data management and report writing | * | * | * | * |  |  | ✓ |  | 75,000 |  |  |  | GHS | CAD |  |
|  |  | 82 | Organize Safe motherhood activities twice in the year | Four sub-Municipal | - | Safe motherhood activities organized | * | * | * | * |  |  |  |  | 30,000 |  |  |  | GHS | CAD |  |
|  |  | 83 | Conduct EPI activities | Six Sub-district | - | To strengthen routine Immunizations | * | * | * | * |  |  | ✓ |  |  |  |  |  | GHS | CAD |  |
|  |  | 84 | Conduct quarterly monitoring Supervision | Six Sub-district | 4 | Monitoring and Supervision conducted | * | * | * | * |  |  | ✓ |  | 30,000 |  |  |  | GHS | CAD |  |
|  |  | 85 | Conduct TB Case detection and screening on daily basis | Six Sub-district |  | TB screening conducted | * | * | * | * | * |  | ✓ |  | 30,000 |  |  |  | GHS | CAD |  |
|  |  | 86 | Organise HIV/AIDS control and management in the district | Two Sub-district | - | Creating ART sites at two health Centers | * | * | * | * | * |  | ✓ |  |  |  |  | 20,000 | GHS | JSI, CAD |  |
|  |  | 87 | Conduct PMTCT/HTC monthly | Six Sub-district | - | HTC services | * | * | * | * |  |  | ✓ |  | 2000 |  |  |  | GHS | CAD |  |
|  |  | 88 | Organise community and radio education on NHIS | Municipal Wide | - | Number of community and radio education in school organized | * | * | * | * |  |  | ✓ |  |  | 5,000.00 |  |  | NHIA | CAD, Media |  |
|  |  | 89 | Repairs of Office Equipment | Goaso | - | Office equipment repaired | * | * | * | * |  |  | ✓ |  |  |  |  |  | NHIA | CAD |  |
|  |  | 90 | Visit to Communities, Schools & Institutions for Registration on NHIS | Municipal Wide | - | Communities, schools and Institutions registered | * | * | * | * |  |  | ✓ |  |  | 1,500 |  |  | NHIA | CAD |  |
| Focus Area: Water and Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Environmental health and sanitation services | 91 | Conduct Premises & institutional inspection | Municipal wide |  | No of Premises Inspected | * | * | * | * |  |  | ✓ |  |  | 5,000 | 2,000 | 700 | CAD (EHU) | MA,Zoomlion,traditional authorities, households, communities |  |
|  |  | 92 | Solid waste management and supervision | Municipal wide |  | % of solid waste collected | * | * | * | * |  |  | ✓ |  |  | 190,000 |  |  | CAD (EHU) | Zoomlion, MDH,MDE,Traditionalauthorities,communities |  |
|  |  | 93 | Conduct Mass spraying of sanitary sites | Municipal Wide |  | No of sites sprayed | * | * | * | * |  |  | ✓ |  |  | 170,000 |  |  | CAD (EHU) | MA,MDH, Food /water vendors |  |
|  |  | 94 | Evacuation of heaped refuse in various communities and desilting | Municipal wide |  | % of communities covered | * | * | * | * |  |  | ✓ |  |  | 130,000 |  |  | CAD (EHU) | Zoom lion, traditional authorities, individual household, private sector |  |
| Social Services Delivery | Environmental Health and Sanitation Services | 95 | Organize sensitization Promotion of CLTS and construction of household latrines | Major communities |  | No. sensitization programs on construction of households latrines | * | * | * | * |  |  | ✓ |  |  | 10,000 |  |  | CAD (EHU) | Assembly Members, MEDIA |  |
|  |  | 96 | Evacuation of refuse Dump | Mim Zongo |  | Refuse Dump evacuated | * | * | * | * |  |  | ✓ |  |  |  | 295,252.00 |  | CAD (EHU) | Zoomlion, Mim Zonal Council |  |
|  |  | 97 | Facilitate organization of regular clean-up exercise | 10 Selected communities |  | No of clean up exercises organized | * | * | * | * |  |  | ✓ |  | 68,921 |  |  |  | CAD (EHU) |  |  |
|  |  | 98 | Arrest and control of stray animals | Major communities |  | No of stray animal arrested | * | * | * | * |  |  | ✓ |  |  | 8,700 |  |  | CAD (EHU) | CAD |  |
|  |  | 99 | Conduct Medical screening of food vendors | Major communities |  | No of venders screened | * | * | * | * |  |  | ✓ |  |  |  | 7,809 |  | CAD (EHU) | CAD |  |
|  |  | 100 | education and formation of sanitation clubs in schools | Municipal wide |  | No. of education on formation of sanitation clubs in schools done | * | * | * | * |  |  | ✓ |  |  | 6,900 |  |  | CAD (EHU) | Fin. Dept, GES, FM Stations |  |
|  |  | 101 | Mechanization of 1No borehole at Ayomso | Ayomso | - | 1No. bore mechanism |  |  | * |  | ✓ |  |  |  | 70,000.00 |  |  |  | CWSA | MA, Ayomso Zonal council |  |
|  |  | 102 | Water quality monitoring | Ayomso, Goaso, Mim | 1 | No. of water quality monitored |  |  | * |  |  |  | ✓ |  | 31,000.00 |  |  |  | CWSA | MA |  |
|  |  | 103 | Reconstruction of Goaso water system | Goaso |  | Goaso water system reconstructed | * | * | * | * |  |  | ✓ |  |  |  | 48,824,990.49 |  | CWSA | MA |  |
|  |  | 104 | Monitoring of CWSA water systems | Ayomso, Goaso, Mim |  | CWSA water systems monitored | * | * | * | * |  |  | ✓ |  |  |  | 1,859,385.64 |  | CWSA | MA |  |
| Thematic Area/ Development Dimension: Environment, Infrastructure, and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area : Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enviromental Management | Disaster Prevention and management | 105 | Develop, Implement and Update Climate Change & Disaster Risk Management Action Plans | Municipal Wide | - | Climate Change and Disaster Risk Management Plan developed and updated | * | * | * | * | ✓ |  |  |  |  |  |  | 11,566,071 (UDG) | NADMO,GNFS/Forestry Division/Dept of Agric | CAD, Fin. Dept, NCCE |  |
|  |  | 106 | Conduct Anti-Bush fire Campaigns | Municipal wide | 1 | No. of Communities educated and sensitized | * |  |  |  |  |  | ✓ |  | 1,600.00 |  | 700.00 |  | NADMO | NCCE CAD, Fin Dept, FSD, Dept of Agric, GNFS |  |
|  |  | 107 | Monitoring of Anti-Bushfire and Scooping Activities | Municipal wide |  | No. of Communities monitored | * |  |  |  |  |  | ✓ |  | 2,500.00 |  | 700.00 |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
|  |  | 108 | Organize Public education on rainstorms, flooding, and inspection of buildings on areas liable to flooding | Municipal Wide |  | No. of Communities educated on flooding, rainstorms | * |  |  |  |  |  | ✓ |  | 1,200.00 |  |  |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
|  |  | 109 | Training of NADMO staff on climate change & disaster risk reduction, hazard mapping and first aid | Goaso |  | No. of staff trained |  | * |  |  |  |  | ✓ |  | 1,500.00 |  | 500.00 |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
|  |  | 110 | Sensitization on effects of climate change on agriculture | Municipal Wide |  | Thirty five (35) communities sensitized |  | * |  |  |  |  | ✓ |  | 2,000.00 |  | 400.00 |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
| Focus Area : Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 111 | Sensitization program on biodiversity and ecosystem | Municipal wide | 1 | No. of Communities sensitized |  |  | * |  |  |  | ✓ |  | 3,000.00 |  | 700.00 |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
|  |  | 112 | Organize Tree planting (Green Ghana Day)on public institutional lands and river banks | Municipal wide |  | No. of trees planted |  |  | * |  |  |  | ✓ |  | 2,000.00 |  | 400.00 |  | FSD | MA, NADMO, NCCE, CSOs |  |
|  |  | 113 | Conduct Training and monitoring activities of DVGs | Municipal Wide |  | Seven DVGs trained and monitored |  |  | * |  |  |  | ✓ |  | 500.00 |  | 200.00 |  | NADMO | Forestry Com. MA |  |
|  |  | 114 | Organize Community durbar on Bushfires | Goaso |  | 260 stakeholders educated |  |  |  | * |  |  | ✓ |  | 2,200.00 |  | 500.00 |  | NADMO | ♦Forestry Com. MA |  |
|  |  | 115 | Educating and sensitizing saw millers and artisans on safety precautions and other occupational hazards | Municipal Wide |  | 80% of the saw millers and artisans educated |  |  |  | * |  |  | ✓ |  | 2,000.00 |  | 400.00 |  | NADMO | ♦Forestry Com. MA |  |
|  |  | 116 | Education on bushfires and other harmattan related disasters as well as road and accidents. | Municipal Wide |  | No. of communities educated |  |  |  | * |  |  | ✓ |  | 2,800.00 |  | 600.00 |  | NADMO | ♦Forestry Com. MA |  |
| Focus Area: Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 117 | Organize environmental health programmes (air pollution, water pollution, noise pollution recreation of mash land etc.) | Major communities |  | No. of environmental health programs | * | * | * | * |  |  | ✓ |  |  |  | 8,000 |  | EHU | MHU,EPA,Zoomlion,PPD,traditional authorities, communities |  |
|  |  | 118 | Support to Reduce Emission from Deforestation and Degradation (REDD+ ) activities | Municipal Wide |  | No. of REDD+ Activities supported | * | * | * | * | ✓ |  |  |  |  |  |  | 65,548.68 | CAD | FSD GNFS, , NADMO |  |
|  |  | 119 | Education on effects of emission of carbon monoxide from vehicles and other industrial machines | Municipal Wide |  | Communities, drivers and factory workers educated |  | * |  |  |  |  | ✓ |  | 2,800.00 |  | 400.00 |  | NADMO | CAD, Fin Dept, GNFS, NCCE, Forestry Division |  |
| Focus Area: Human Settlement Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment , Infrastructure, and Human Settlement | Physical/Spatial Planning | 120 | Produce Local Plans for new areas | Abebrese, Alikrom and Mim sector 2 Extension | 3 | Number of local plans for new areas produced | * | * | * |  |  |  | ✓ |  | 7,000.00 |  |  |  | PPD | MSPC Members Traditional Authorities |  |
|  |  | 121 | Mount 20 and 50 number street Address poles in Goaso and Mim respectively | Goaso Sector 4,sector 4 extension and Mim sector 7 | 3 | Number of street Address poles mounted | * | * | * |  |  |  | ✓ |  | 2,340.00 |  |  |  | PPD | MSPC Members Traditional Authorities |  |
|  |  | 122 | Prepare 20-Year Municipal Spatial Development Framework (SDF) and Structure Plans for Goaso and Mim | Goaso and Mim | - | Number of municipal spatial development framework and structure plan prepared | * | * | * | * | ✓ |  |  |  |  |  |  | 145,714.3(UDG) | PPD | CAD |  |
|  |  | 123 | Update and map-out basic services (roads, pedestrian walkways, streets, drainage, electricity/streetlights, solid waste/sanitation, water) in urban areas | Goaso and Mim |  | No. of basic services (road, street, drainage, electricity etc.) updated | * | * | * | * | ✓ |  |  |  |  |  |  | 52,500.01 (UDG) | PPD | CAD |  |
|  |  | 124 | Erect 45No. Sinages and update SNPAS database | Goaso and Mim |  | No. of Sinages erected and SNPAS database updated | * | * | * | * | ✓ |  |  |  |  |  |  | 114,428.57 (UDG) | PPD | CAD |  |
|  |  | 125 | Organize training in Digital Planning and Map Making | Goaso |  | No. of digital Planning and Map Marking training organized | * | * | * | * | ✓ |  |  |  |  |  |  | 34,285.71 (UDG) | PPD | CAD |  |
|  |  | 126 | Update business inventory and register/database (referenced with Property Addressing -SNPAS) | Municipal Wide |  | Number of Business inventory and Register updated | * | * | * | * | ✓ |  |  |  |  |  |  | 26,107.15 (UDG) | PPD | CAD, Fin. Dept. |  |
|  |  | 127 | Organize monthly Statutory Planning Committee meeting (Technical Subcommittee and Municipal Spatial Planning Committee) | Municipal Assembly Conference Hall | 24 | All monthly meetings organized | * | * | * | * |  |  | ✓ |  |  |  | 6,200.00 |  | M.A PPD | TSC/MSPC Members |  |
|  |  | 128 | Sensitize the general public (T.A on Physical Planning related issues) | Fawohoyeden, Fetagya, Goaso, Asuadai, FM stations | 5 | Number of Sensitization Programme held | * | * | * | * |  |  | ✓ |  | 2,800.00 |  | 2,900 |  | PPD | CAD FM Station Dechem Traditional Council Fawohoyeden Community |  |
|  |  | 129 | Conduct Monthly site Inspections | Goaso, Mim, Asumura,Akrodie,Kasapin, Dechem,Ayomso, Bediako,Dotom | 12 | Monthly inspections conducted | * | * | * | * |  |  | ✓ |  |  |  | 1,200.00 |  | PPD | EPA, GNFS, Budget, Planning, Traditional Authority |  |
|  |  | 130 | Pruning, Mowing and Nursing of seedlings | Municipal Assembly,MCE and MCD’s residence | Daily | No. of Pruning, Mowing and seedlings done | * | * | * | * |  |  | ✓ |  | 860.00 |  | 900.00 |  | PPD | Parks & Garden, forestry |  |
| Focus Area: Public Works, Rural Housing and Water Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 131 | Complete construction of 8- unit kitchen facility for Ghana Police Service | Goaso |  | Kitchen facility constructed for Ghana police service | * | * | * | * |  |  | ✓ |  | 10,000.05 |  |  |  | Works Dept | CAD,GPS |  |
|  |  | 132 | Support Community initiated projects (Self Help Projects) | Municipal wide |  | No. of community initiated projects supported | * | * | * | * |  |  | ✓ |  |  | 70,558.59 |  |  | CAD | Fin Dept, Works Dept |  |
|  |  | 133 | Complete payment for the drilling and mechanization of borehole with 10,000 litres capacity polytank at the District Magistrate’s bungalow | Goaso |  | drilling and mechanization of borehole with 10,000 litres capacity polytank at the District Magistrate’s bungalow completed | * | * | * | * |  |  | ✓ |  |  | 49,091.68 |  |  | Works Dept | CAD |  |
|  |  | 134 | Complete Payment for the renovation of the Area Council Office at Mim | Mim | - | Payment of Urban Council Office completed | * | * | * | * |  |  | ✓ |  |  |  | 251,277.56 |  | Works Dept | CAD |  |
|  |  | 135 | Repairs and Maintenance of existing water facilities in the Municipality | Municipal wide |  | No. of water facilities in the repaired and maintained | * | * | * | * |  |  | ✓ |  | 40,000.00 |  |  |  | Works Dept | CAD |  |
|  |  | 136 | Maintenance of street lights in the Municipality | Municipal wide |  | No. of street lights in maintained | * | * | * | * |  |  | ✓ |  | 200,000.00 |  |  |  | Works Dept | CAD |  |
|  |  | 137 | Renovation of Assembly Hall | Goaso |  | Level of renovation done | * | * | * | * | ✓ |  |  |  |  | 285,000.00 |  |  | Works Dept | CAD |  |
|  |  | 138 | Complete extension and re-molding of administration block | Goaso |  | Level of work done executed on Administration block | * | * | * | * |  |  | ✓ |  |  | 315,389.71 |  |  | Works Dept | CAD |  |
|  |  | 139 | Renovation/ furnishing of selected revenue offices & erection of Kiosk at revenue check point | Municipal wide | 4 | No of renovations conducted | * | * | * | * | ✓ |  |  |  | 20,000 |  |  |  | Finance Department | Central Adminstration |  |
|  |  | 140 | Grading & patching of Roads by Hon. MP. | Municipal wide |  | Roads patched and graded | * | * | * | * |  |  | ✓ |  |  | 70,000.00 |  |  | Works Dept | CAD,MP |  |
|  |  | 141 | Grading & patching of 170KM Roads within the Municipality | Municipal wide |  | Roads patched and graded | * | * | * | * | ✓ |  |  |  |  | 45,000.00 | 224,370.68 |  | Works Dept | CAD,DUR |  |
|  |  | 142 | MP'S Support to Rural Electrification | Municipal wide |  | Rural electrification supports by MP | * | * | * | * |  |  | ✓ |  |  | 100,000.00 |  |  | Works Dept | CAD,NEDCO |  |
|  |  | 143 | Completion of Infrastructural Projects in the Constituency by the HON. MP | Municipal wide |  | Infrastructural projects completed by MP | * | * | * | * |  |  | ✓ |  |  | 180,000.00 |  |  | Works Dept | CAD |  |
|  |  | 144 | Provide counterpart funding for 3No. water project | Akrodie, Kasapin, Fawohoyeden |  | Counterpart funding provided for Safe water projects | * | * | * | * | ✓ |  |  |  |  | 1,650,000.00 (SW,WV) |  |  | CAD | Finance Dept., Works Dept., Zonal Councils |  |
|  |  | 145 | Construction of 500M Storm Drain at Manhyia, Pavement of Daily Market and Old Station, construction of fenced wall, construction of 2No. Passenger Sheds and construction of 1No. 10-Seater Water Closet Toilet Facility and Upgrading of 3.2Km Goaso Town Roads (Abotanso, Ahafoman SHS Road, NHIA-Petlinda Road, Pentecost Church-Salem Assembly Junction Road, SSNT-Omanhene Residence Junction Road, Assembly Office -MCE’s Residence, Magistrate’s Residence to-Nananom FM-MCD’s Residence) | Goaso |  | Construction works carried out | * | * | * | * | ✓ |  |  |  |  |  |  | 9,430,581.6(UDG) | Wks Dept, | MLGDRD, CAD, Fin Dept, Traditional Authorities, Assembly Members, Urban Roads, Highways EPA, Consultants, RCC, GPRTU, Plantain Market traders, Zoomlion, |  |
|  |  | 146 | Supervise the construction, renovation/ rehabilitation of physical development projects | Municipal wide |  | No. of constuction of Physical projects supervised | * | * | * | * |  |  | ✓ |  | 2,000.00 | 2,000.00 | 2,000.00 |  | Works Dept | CAD. Fin Dept. |  |
|  |  | 147 | Procurement of Digital slit Hammer test, calipers for measuring of roofs and safety equipment | Municipal wide |  | No. of digital slit hammers, calipers and safety equipment procured | * | * | * | * |  |  | ✓ |  | 10, 000.00 | 11,000.00 |  |  | Works Dept | CAD. Fin Dept. |  |
|  |  | 148 | Organize quarterly site meetings with stakeholders | Municipal Assembly |  | No. of site meetings organized | * | * | * | * |  |  | ✓ |  | 1,500.00 |  | 2,000.00 |  | Works Dept | CAD. Fin Dept. |  |
|  |  | 149 | Collect data on Feeder roads | Municipal wide |  | No. of Data on Feeder roads collected | * | * | * | * |  |  | ✓ |  | 1,000.00 | 1,000.00 | 1,000.00 |  | Works Dept | CAD. Fin Dept., URD |  |
|  |  | 150 | Conduct building inspectorate exercise on all approved permit and Collect data on Temporal Structures | Municipal wide |  | No. of building inspection exercises conducted to | * | * | * | * |  |  | ✓ |  | 1,000.00 | 2,000.00 | 1,000.00 |  | Works Dept | CAD. Fin Dept., PPD |  |
|  |  | 151 | Take inventory of non- functional boreholes and schools that needs rehabilitation/ renovation | Municipal wide |  | No. of inventory on non- functional boreholes and schools that needs rehabilitation taken | * | * | * | * |  |  | ✓ |  | 2,000.00 | 5,000.00 | 2,000.00 |  | Works Dept | CAD. Fin Dept.,CWSA,GES |  |
| Focus Area: Transportation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Road and Transport Services | 152 | Organize quarterly Radio sensitization programmes on proper traffic regulation in the Municipality | Municipal Wide | 4 | No of radio sensitization programmes organized | * | * | * | * |  |  | ✓ |  |  |  | 2,000.00 |  | CAD (Transport Dep’t) | NRSA |  |
|  |  | 153 | Maintenance and purchase of fuel and lubricants for official vehicles (7.) and Motor Bikes (14) | Goaso | 7 vehicles and 7motor bikes maintained And provided with fuel | Number of vehicles and Motor bikes maintained /Amount of fuel purchased | * | * | * | * |  |  | ✓ |  | 2,500 | 27,000 | 355,500.00 |  | CAD (Transport Dept) | Finance Dept, MWD, Agric. Dept |  |
|  |  | 154 | Insure 6 MA vehicles and 7 motorbikes | Goaso | 2 vehicles insured | Number of vehicles and motorbikes insured | * | * | * | * |  |  | ✓ |  |  |  | 30,000.00 |  | CAD (Transport Dept) | Transport Dept |  |
| Thematic Area/Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance and Audit | 155 | Conduct monthly Audit on Payroll Management Reviews, Cash and Revenue Management, Asset Management, Transport Management , Procurement /Stores Management) | Goaso |  | No. of monthly audits conducted No. of management areas audited | * | * | * | * |  |  |  | ✓ |  |  | 4,250.00 | 1,200.00 | CAD (IAU) | MOFA, Finance, Revenue, Estate Officer and Stores, Transport Unit, Procurement Unit |  |
|  |  | 156 | Attend Capacity Building programmes | Goaso and Out of Goaso | 2 | No. of Capacity building Programs attended | * | * | * | * |  |  |  | ✓ |  | 6,000.00 | 3,500.00 | 800.00 | CAD (IAU) | GIZ, IAA, LGS |  |
|  |  | 157 | Purchase value books | Goaso | 4 | No. of Value books purchased | * | * | * | * |  |  |  | ✓ | 2,000 |  |  |  | Finance department | Central Administration |  |
|  |  | 158 | Pay ex-gratia of Assembly members | Goaso | - | No. of Assembly Members paid. | * | * | * | * |  |  |  | ✓ |  | 84,000.00 |  |  | Fin.Dept. | Assembly Members |  |
| Focus Area: General Administration and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | 159 | Hold Sub-committee, Executive Committee ,Management Meetings, Assembly meetings and Audit committee meetings | Goaso | 16 | No. of meetings held | * | * | * | * |  |  |  | ✓ |  |  | 138,730.00 |  | CAD (Admi) | Fin. Dept., Assembly Members,Other Depts |  |
|  |  | 160 | Hold 12 No. heads of departments meetings | Goaso | 4 | No. of HOD meetings held | * | * | * | * |  |  |  | ✓ |  |  | 5,000.00 |  | CAD (Admi) | Other Depertments |  |
|  |  | 161 | Hold 12 No MUSEC meetings, 4No. MEOC and health committee meetings | Goaso | 20 | No. of MUSEC,MEOC and Health committee meetings held | * | * | * | * |  |  |  | ✓ |  |  | 31,680.00 |  | CAD(Admi) | Security Services (GPS, GNFS, BNI), TAs |  |
|  |  | 162 | Organize National Days Celebrations (Independence Day, Mayday, Farmers ‘Day) etc | Municipal wide | 3 | National Days Organized | * | * |  | * |  |  |  | ✓ |  | 111,960.00 | 17,000.00 |  | CAD(Admi) | Other relevant departments |  |
|  |  | 163 | Support religious festivities (X’mas, Easter, Eidlfitr, Eid Adha, etc.) | Municipal wide | 3 | No. of religious festivities supported | * | * | * | * |  |  |  | ✓ |  | 105,560.00 |  |  | CAD | Religious Groups, Fin. Dept. |  |
|  |  | 164 | Organize 1 No. capacity building programmes for caterers and selected teachers of the beneficiaries schools of the Ghana School Feeding programme and renew health certificates for 41 caterers | Goaso | 1 | 1No. of capacity building programme organized and No. of health certificate renewed |  |  |  | * |  |  |  | ✓ |  |  | 5,050.00 |  | CAD(Admi) | GES, Fin. Dept. EHU |  |
|  |  | 165 | Service contingency activities | Goaso | - | No. of contingency activities serviced | * | * | * | * |  |  |  | ✓ |  | 150,000.00 |  |  | CAD(Admi) | Fin. Dept. |  |
|  |  | 166 | Build capacity of Zonal Councils and build capacity of Assembly members | Municipal wide | - | No. of members supported | * | * | * | * |  |  |  | ✓ |  | 60,000.00 |  |  | CAD(Admi) | Zonal/Urban Councils, Fin. Dept. |  |
|  |  | 167 | Cater for protocol services (hosting of official guests) | Goaso | - | Protocol services provided for | * | * | * | * |  |  |  | ✓ |  |  | 50,600.00 |  | CAD(Admi) | Fin. Dept. |  |
|  |  | 168 | Pay NALAG dues/contributions | Goaso | - | NALAG dues/contributions paid for | * | * | * | * |  |  |  | ✓ |  |  | 5000.00 |  | CAD(Admi) | Fin. Dept. |  |
|  |  | 169 | Service office utility bills (Electricity, water, Telecommunication and Postings) | Goaso | - | Expenditure on office utilities done | * | * | * | * |  |  |  | ✓ |  |  | 26,000.00 |  | CAD(Admi) | Fin. Dept |  |
|  |  | 170 | Hold 4 No. Audit Committee meetings | Goaso | 4 | No. of Audit Committee meetings organized | * | * | * | * |  |  |  | ✓ |  |  | 20,000.00 |  | CAD(Audit Unit) | Fin. Dept. |  |
|  |  | 171 | Organize town hall meetings/forum and MCE visits to communities to promote Social Accountability/Public Education and Sensitization | Municipal Wide | 4 | No. of communities visited and Town hall meeting, MCE visits Organised | * | * | * | * |  |  |  | ✓ |  |  | 20,000.00 |  | CAD(Admi) | Fin. Dept. |  |
|  |  | 172 | Build the capacity of Administrative Officers | Goaso |  | Administrative Officers trained |  | * | * |  |  | ✓ |  |  |  |  | 5,000 |  | CAD | HRD |  |
|  |  | 173 | Inauguration of 8th Municipal Assembly | Goaso |  | Assembly members Inaugurated | * |  |  |  |  | ✓ |  |  |  | 50, 000.00 |  |  | CAD | Other Depts, Assembly Members |  |
|  |  | 174 | Carry out Consultancy Services (Designs and Supervision) | Goaso |  | No. of consultancy services carried out | * | * | * | * |  | ✓ |  |  |  |  |  | 2,583,988.29(UDG) | MLGDRD/Consultant | MA, Works Dept, Market Women, Traditinal Authorities, GPRTU, Zoomlion, EPA, Consultants, RCC |  |
|  |  | 175 | Update business inventory and register/database (referenced with Property Addressing -SNPAS) | Municipal Wide |  | Number of Business inventory and Register updated | * | * | * | * |  | ✓ |  |  |  |  |  | 26,107.15 (UDG) | CAD(Admi) | Fin. Dept. |  |
| Focus Area: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Administration and management | Human Recourse Management | 176 | Organise Capacity Building Trainings on Local Government Protocols, Procurement Audit, Revenue Mobilization, I.T Systems, Agric, E- Records & file management, semi current records &Prosecution& Inspection, GHANEPS and project Management | Goaso | 2 | No. of Trainings Organized | * | * | * | * |  |  |  | ✓ |  | 7,000.00 | 15,000.00 | 6,600.00 | HRD | CAD, Fin. Dept., EHU, Revenue Database, Procurement, Dept of Agric |  |
|  |  | 177 | Submission of quarterly reports | Goaso | 4 | Reports Submitted | * | * | * | * |  |  |  | ✓ |  |  | 200 |  | HRD | CAD, Fin. Dept. |  |
|  |  | 178 | Validate monthly salaries | Goaso | 12 | Salaries Validated | * | * | * | * |  |  |  | ✓ |  |  | 600 |  | CAD (HRD) | Fin. Dept. |  |
|  |  | 179 | Organize refresher training for all staff on Local Governance Act, PFM Act, Public Procurement Act, Public Private Partnership Act, Local Government Service Protocols, | Goaso |  | Number of trainings organised | * | * | * | * |  | ✓ |  |  |  |  |  | 72,428.57 (UDG) | CAD (HRD) | Fin. Dept. |  |
| Development Dimension: Implementation, Co-ordination, Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Production and Utilization of Statistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Administration and management |  | 180 | Conduct quarterly market reading (Consumer Price Index | Municipal wide | 12 | Number of Market readings conducted | * | * | * | * |  |  |  | ✓ | 3,500 |  |  |  | Statistics Department | Central Administration and GSS |  |
|  |  | 181 | Update Business Register Monthly | Municipal wide | 12 | Number of businesses registered | * | * | * | * |  | ✓ |  |  | 3,500 |  |  |  | Statistics department | Central Administration |  |
|  |  | 182 | Collection and Dissemination of Administrative data | Municipal wide | 12 | No. of Administrative data disseminated | * | * | * | * |  |  |  | ✓ | 1,000 |  |  |  | Statistics department | Central Administration and GSS |  |

|  | Planning, Budgeting, Coordination and Statistics | 183 | Coordinate implementation of 2024 CAAP and thematic plans (UDAP 2024, WASH, NACAP, RIAP, LED Plan, GovID, PPS,MESSAP) | Goaso | 4 | No of plans coordinate d and implemented | * | * | * | * |  | ✓ |  | 20,000.00 | 30,000.00 | 20,000.00 | CAD(Planning Unit) | Other Depts,NGOs/CSOs, IRC, MLGDRD, LGS, RCC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 184 | Hold 4 quarterly MPCU meetings, 3 Planning sessions | Goaso | 3 | No. MPCU meeting organized | * | * | * | * | ✓ |  |  |  | 7,000.00 |  | CAD(Planning Unit) | Other Depts, NGOs/CSOs, IRC, LGS |
|  |  | 185 | Conduct MPCU and Departmental Monitoring and Evaluation of programmes and projects, Conduct safeguards, and Review implementation 2024 CAAP | Goaso | 3 | No. of projects and programs monitored and review of the CAAP conducted | * | * | * | * |  | ✓ |  | 1,158,095.54 | 1,158,095.54 | 645,997.08 (UDG) | CAD (Planning Unit) | CAD,DEPT OF AGRIC Other Depts,NGOs/CSOs, MLGDRD, IRC |
|  |  | 186 | Organize quarterly Budget committee meetings | Goaso | 3 | No. of quarterly budget committee meetings conducted | * | * | * | * |  | ✓ |  |  | 10,000 |  | CAD(Budget ) | Other Depts,NGOs/CSOs |
|  |  | 187 | Organize quarterly and Mid-Year review meetings of Procurement plan | Goaso | 1 | No. of reviews done | * | * | * | * |  | ✓ | 2,000 |  |  |  | CAD( Planning Unit) | Other Depts,NGOs/CSOs |
|  |  | 188 | Organize training for MPCU members in Urban Planning and Management, Monitoring and Evaluation, Environmental, Social and Project Impact Assessment and Safeguards | Goaso | - | Number of trainings for MPCU members in urban planning and management organized | * | * | * | * | ✓ |  |  |  |  | 48,571.43 (UDG) | CAD Planning Unit) | Other Depts,MPCU MEMBERSNGOs/CSOs, IRC, RCC |
|  |  | 189 | Conduct Mid-Term Review of 2022-2025 MTDP | Goaso | - | Mid-term review of MTDP carried out | * | * | * | * | ✓ |  |  |  |  | 60,714.28 (UDG) | CAD (Planning Unit) | Other Depts,NGOs/CSOs, MLGDRD, IRC |
|  |  | 190 | Support preparation of 2026-2029 DMTDP | Goaso |  | 2026-2029 DMTDP prepared | * | * | * | * | ✓ |  |  |  |  | 60,714.29 (UDG) | CAD (Planning Unit) | Other Depts,NGOs/CSOs, MLGDRD, Zonal Councils |
|  |  | 191 | Repairs of office equipment | Goaso |  | No. of office equipment repaired | * | * | * | * |  | ✓ |  |  |  |  | CAD (Procurement) | Other Depts. |
|  |  | 192 | Procurement and Distribution of 1,100 Wooden Dual Desks and 400 Mono desk | Municipal wide |  | No. of wooden Desks procured | * | * | * | * | ✓ |  |  |  |  | 444,000.00 | CAD (Procurement) | GES |
|  |  | 193 | Procurement and Installation of 100 KVA transformer and Accessories at the 1D1F Plantain Processing Factory | fawohoyeden |  | Transformer and Accessories at the 1D1F Plantain Processing Factory procured | * | * | * | * | ✓ |  |  |  |  | 134,500.00 | CAD (Procurement) | Dept. of Agric |
|  |  | 194 | Procurement of 280 Electrical Poles | Municipal wide |  | No. of electrical poles procured | * | * | * | * | ✓ |  |  |  |  | 559,790.00 | CAD (Procurement) | NEDCO |
|  |  | 195 | Procure 8No. Laptop computers, 12No. Desktop computers, 2No. Photocopier, 1No.GPS, 5No. Printer, 1No. Projector Screen, 2No File Cabinets, 15No. swivel chairs,1 Camera,2No. UPS,5 giant stable, 5 combiner,2No. internet Router | Goaso |  | Number of laptop computers, desktop computers, photocopier, GPS, printer, projector procured | * | * | * | * | ✓ |  |  |  |  | 185,535.7 (UDG) | CAD (Procurement) | Other Depts. |
|  |  | 196 | Organize Public Sensitization on Government Policies, Assembly’s Budget fees and fines & all activities | Municipal Wide | - | No. of Public Sensitization organised | * | * | * | * |  | ✓ |  |  | 2,500 |  | ISD | CAD, Media |
|  |  | 197 | Organize Publications of development activities of the Assembly on TV, Radio & Online and report coverage of Assembly Activities | Municipal Wide | - | Development Activities published | * | * | * | * |  | ✓ |  |  | 2,950 |  | ISD | CAD, Media |
| SUB-TOTALS |  |  |  |  |  |  |  |  |  |  |  |  | 891,021.00 | 11,147,473.54 | 53,754,618.22 | 35,262,683.69 |  |  |
| GRAND TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 101,055,796.45 |  |  |  |  |  |